## Unit Tracking
FORSYTHE II
All Units
Unit Number | Vegetation Treatment | Phase | Unit Acres | Treatment Acres | GPS Acres | Treatment Method | Slash Treatment | Step Transect Provided | Unit Boundary Flagged | Unit Boundary Painted | Draft Rx Provided | Sample Mark Completed | Final Rx Provided | Tree Marking Completed | Cruise Method Used | Cruise Completed | Crosswalk Review | Unit Maps Completed | Appraisal Completed | Timber Sale Report | Contract Package Draft | MMG Contract Review | Contract Officer Review | Contract to AQM | Contract Awarded | Contract Started | Contract Completed | Post Step Transect Provided | Comments
1 | Lodgepole Pine Treatment | 3 | 15 | 4.5 | 6.3 | Manual | Chip and/or pile & burn | 2018-07-10 | 2018-08-29 | [5 empty] | Fix 1/50th | 2018-11-01 | In Progress | [11 empty] | 4.2 acres of patchcut; 4.5 acres of aspen aggregations
2 | Lodgepole Pine Treatment | 3 | 49 | 14.7 | 4.5 | Manual | Chip and/or pile & burn | 2018-07-10 | 2018-09-05 | [5 empty] | Fix 1/50th | 2018-11-01 | In Progress | [11 empty] | Removed from Phase II Mechanical to Phase 1 Manual 6/14/2018
3 | Lodgepole Pine Treatment | 1 | 31 | 9.3 | 7.4 | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2018-07-10 | 2018-08-27 |  | 2018-10-02 | NA |  | NA | Fix 1/50th | 2018-11-01 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [5 empty] | Removed from Phase II Mechanical to Phase 1 Manual 8/27/2018
4 | Lodgepole Pine Treatment | 1 | 64 | 19.2 | 11.5 | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2018-07-10 | 2018-08-28 |  | 2018-11-02 | 2018-10-05 |  | 2018-11-06 | Fix 1/50th | 2018-11-01 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [5 empty] | Removed from Phase II Mechanical to Phase 1 Manual 8/27/2018; DF Mixed Conifer Aggregation sample mark completed; Aggregation needs to be painted. Aggregation marked.
5 | Aspen Restoration | 1 | 17 | 17 | 17 | Manual | Chip and/or pile & burn | NA | 2018-10-25 | NA | 2017-12-05 | NA |  | NA | Fix 1/20th | 2018-02-12 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [5 empty] | Unit was identified as flagged on 12/5/2017; not fully completed
7 | Aspen Restoration | 1 | 9 | 9 | 8 | Manual | Chip and/or pile & burn | NA | 2018-10-25 | NA | 2017-12-05 | NA |  | NA | Fix 1/20th | 2018-02-12 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [5 empty] | Unit was identified as flagged on 12/5/2017; not fully completed
8 | Aspen Restoration | 1 | 7 | 7 | 6 | Manual | Chip and/or pile & burn | NA | 2018-10-25 | NA | 2017-12-05 | NA |  | NA | Fix 1/20th | 2018-02-12 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [5 empty] | Unit was identified as flagged on 12/5/2017; not fully completed
9 | Douglas-fir Mixed Conifer Treatment | 4 | 156 | 156 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
10 | Lodgepole Pine Treatment | 4 | 28 | 8.4 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
11 | Lodgepole Pine Treatment | 4 | 20 | 6 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
12 | Douglas-fir Mixed Conifer Treatment | 4 | 7 | 7 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
14 | Lodgepole Pine Treatment |  | 35 | 10.5 |  | Mechanical/ Manual | Remove off-site and/or chip and/or masticate and/or pile & burn
15 | Aspen Restoration |  | 21 | 21 |  | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn
16 | Lodgepole Pine Treatment |  | 26 | 7.8 |  | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn
17 | Lodgepole Pine Treatment |  | 26 | 7.8 |  | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn
18 | Meadow/Shrubland Restoration |  | 8 | 8 |  | Manual | chip and/or pile & burn
19 | Lodgepole Pine Treatment |  | 64 | 19.2 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
20 | Aspen Restoration |  | 58 | 58 |  | Mechanical/ Manual | Remove off-site and/or chip and/or masticate and/or pile & burn
21 | Lodgepole Pine Treatment |  | 27 | 8.1 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
22 | Lodgepole Pine Treatment |  | 10 | 3 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
23 | Lodgepole Pine Treatment |  | 21 | 6.3 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
24 | Lodgepole Pine Treatment | 2 | 16 | 4.8 | 4.8 | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2018-07-10 | 2017-12-05 |  | 2017-12-05 | NA |  | NA | Fix 1/50th | 2018-11-05 | In Progress | 2019-03-06 | 2019-02-28 | 2019-02-28 | 2019-03-07 | 2019-03-05 | [6 empty] | 3/5/2019: The MMG and Contract Officer reviews will be occurring simultaneously due to contract deadlines established by AQM.
26 | Lodgepole Pine Treatment | 1 | 122 | 36.6 | 6.6 | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2018-07-10 | 2018-10-12 | NA |  | NA |  | NA | Fix 1/50th | 2018-11-05 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [5 empty] | Unit was identified as flagged on 8/1/2018; not fully completed. Flagging completed 10/12/2018.
27 | Lodgepole Pine Treatment | 2 | 55 | 16.5 | 10 | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2018-07-10 | 2018-10-17 |  |  | NA |  | NA | Fix 1/50th | 2018-11-05 | In Progress | 2019-03-06 | 2019-02-28 | 2019-02-28 | 2019-03-07 | 2019-03-05 | [6 empty] | Unit was identified as flagged on 8/1/2018; not fully completed. Flagging completed 10/17/2018. 3/5/2019: The MMG and Contract Officer reviews will be occurring simultaneously due to contract deadlines established by AQM.
28 | Lodgepole Pine Treatment | 2 | 109 | 32.7 | 32 | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2018-07-10 | 2018-10-19 |  |  | NA |  | NA | Fix 1/50th | 2018-11-05 | In Progress | 2019-03-06 | 2019-02-28 | 2019-02-28 | 2019-03-07 | 2019-03-05 | [6 empty] | Unit was identified as flagged on 8/1/2018; not fully completed. Flagging completed 10/19/2018. 3/5/2019: The MMG and Contract Officer reviews will be occurring simultaneously due to contract deadlines established by AQM.
29 | Lodgepole Pine Treatment | 4 | 164 | 49.2 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
30 | Lodgepole Pine Treatment | 3 | 14 | 4.2 |  | Manual | Chip and/or pile & burn
31 | Lodgepole Pine Treatment | 3 | 73 | 21.9 |  | Manual | Chip and/or pile & burn
38 | Broadcast Burn |  | 747 | 747 |  | Broadcast Burn | Prescribed Broadcast Burn
39 | Douglas-fir Mixed Conifer Treatment | 1 | 59 | 59 | 36 | Manual | Northern portion - Lop/Scatter and Prescribed Broadcast Burn; Southern portion Chip and/or pile & burn | 2018-06-20 | 2018-08-06 | NA | 2018-10-02 | 2018-10-02 |  | 2018-10-11 | Fix 1/20th | 2018-11-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
40 | Douglas-fir Mixed Conifer Treatment | 1 | 106 | 106 | 86 | Manual | Lop/Scatter and Prescribed Broadcast Burn | 2018-06-20 | 2017-10-28 | 2017-11-15 | 2017-10-28 | 2017-10-28 |  | 2018-10-15 | Fix 1/20th | 2018-02-14 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [5 empty] | Portion of unit dropped to address MMG concerns and align with Rx burn.
41 | Meadow/Shrubland Restoration | 1 | 29 | 29 | 22 | Manual | Lop/Scatter and Prescribed Broadcast Burn | NA | 2017-10-28 | 2018-01-05 | 2017-10-28 | 2017-10-28 |  | NA | Fix 1/2 | 2018-02-14 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
42 | Lodgepole Pine Treatment | 1 | 19 | 5.7 | 5.6 | Manual | Chip and/or pile & burn | 2018-06-20 | 2018-07-26 | NA | 2018-10-02 | NA |  | NA | Fix 1/50th | 2018-11-01 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [5 empty] | Removed from Phase II Mechanical to Phase 1 Manual 6/14/2018
43 | Douglas-fir Mixed Conifer Treatment | 3 | 42 | 42 |  | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2018-07-10
44 | Broadcast Burn |  | 198 | 198 |  | Broadcast Burn | Prescribed Broadcast Burn
45 | Douglas-fir Mixed Conifer Treatment | 1 | 131 | 131 | 118 | Manual | Lop/Scatter and Prescribed Broadcast Burn | 2018-06-20 | 2018-07-10 | 2018-07-23 | 2018-11-02 | NA |  | 2018-11-05 | Fix 1/20th | 2018-11-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [5 empty] | Removed from Phase II Mechanical to Phase 1 Manual 6/14/2018. Slash Tx is lop and scatter for Rx burn.
46 | Ponderosa Pine Mixed Conifer Treatment | 1 | 12 | 12 | 5 | Manual | Lop/Scatter and Prescribed Broadcast Burn | 2018-06-20 | 2017-10-28 | 2018-01-05 | 2017-10-28 | 2017-10-28 | 2018-08-31 | 2018-09-07 | Fix 1/20th | 2018-02-14 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [5 empty] | Final Rx same as draft Rx.
47 | Douglas-fir Mixed Conifer Treatment | 3 | 20 | 20 |  | Manual | Chip and/or pile & burn | 2018-07-10
48 | Ponderosa Pine Mixed Conifer Treatment | 3 | 75 | 75 |  | Manual | Chip and/or pile & burn | 2018-07-10
49 | Ponderosa Pine Mixed Conifer Treatment | 3 | 47 | 47 |  | Manual | Chip and/or pile & burn | 2018-07-10
50 | Ponderosa Pine Mixed Conifer Treatment | 1 | 7 | 7 | 6 | Manual | Chip and/or pile & burn | 2018-06-20 | 2017-10-17 | 2018-01-09 | 2018-08-01 | 2018-08-01 | 2018-08-09 | 2018-09-04 | Fix 1/20th | 2018-11-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
51 | Ponderosa Pine Mixed Conifer Treatment | 1 | 89 | 89 | 79 | Manual | Chip and/or pile & burn | 2018-06-20 | 2017-10-17 | 2018-02-09 | 2018-08-01 | 2018-08-01 |  | 2018-08-29 | Fix 1/20th | 2018-11-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [5 empty] | Final Rx same as draft Rx.
52 | Ponderosa Pine Mixed Conifer Treatment |  | 8 | 8 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
53 | Aspen Restoration |  | 16 | 16 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
54 | Mixed Conifer Treatment OG |  | 18 | 18 |  | Mechanical/ Manual | Remove off-site and/or chip and/or masticate and/or pile & burn
55 | Douglas-fir Mixed Conifer Treatment |  | 5 | 5 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
58 | Lodgepole Pine Treatment |  | 26 | 7.8 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
59 | Douglas-fir Mixed Conifer Treatment |  | 14 | 14 |  | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn
60 | Douglas-fir Mixed Conifer Treatment |  | 5 | 5 |  | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn
61 | Aspen Restoration |  | 7 | 7 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
63 | Ponderosa Pine Mixed Conifer Treatment | 1 | 5 | 5 | 2 | Manual | Chip and/or pile & burn | 2018-06-20 | 2018-08-29 | NA | 2018-11-02 | NA |  | NA | Fix 1/20th | 2018-11-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
67 | Aspen Restoration |  | 13 | 13 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
68 | Douglas-fir Mixed Conifer Treatment | 3 | 10 | 10 |  | Manual | Chip and/or pile & burn | 2018-07-10 | [20 empty] | Removed from Phase II Mechanical to Phase 3 Manual 6/14/2018
73 | Ponderosa Pine Mixed Conifer Treatment | 3 | 76 | 76 |  | Manual | Chip and/or pile & burn | 2018-07-10
74 | 2-Staged Mixed Conifer Treatment (Stage 1) | 1 | 44 | 44 | 37 | Manual | 1) pile & burn | NA | 2017-10-05 | 2018-07-27 |  | NA |  | NA | NA | NA | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [5 empty] | Step Transect not provided for Stage 1 (piling) activity. Step Transect will be completed prior to thinning operation. Repainted to exclude drainage and riparian vegetation
74 | 2-Staged Mixed Conifer Treatment (Stage 2) | 1 | 44 | 44 | 37 | Manual | 2) thin and pile & burn
75 | Lodgepole Pine Treatment | 1 | 14 | 4.2 | 2.5 | Manual | Chip and/or pile & burn | 2018-06-20 | 2018-07-26 | NA | 2018-10-02 | NA |  | NA | Fix 1/50th | 2018-11-01 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [5 empty] | Removed from Phase II Mechanical to Phase 1 Manual 6/14/2018
76 | Lodgepole Pine Treatment | 1 | 12 | 3.6 | 3.4 | Manual | Chip and/or pile & burn | 2018-06-20 | 2018-07-26 | NA | 2018-10-02 | NA |  | NA | Fix 1/50th | 2018-11-01 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
77 | Douglas-fir Mixed Conifer Treatment |  | 269 | 269 |  | Mechanical/ Manual | Remove off-site and/or chip and/or masticate and/or pile & burn
80 | Douglas-fir Mixed Conifer Treatment |  | 8 | 8 |  | Mechanical/ Manual | Remove off-site and/or chip and/or masticate and/or pile & burn
81 | Aspen Restoration |  | 12 | 12 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
82 | Regeneration Thin | 1 | 1 | 1 | 0.9 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | 2017-12-05 |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
83 | Regeneration Thin | 1 | 0.4 | 0.4 | 0.4 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
84 | Regeneration Thin within Defensible Space | 1 | 0.3 | 0.3 | 0.3 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
85 | Regeneration Thin | 1 | 1 | 1 | 0.63 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [5 empty] | Unit Dropped - Not enough trees (12/5/2017); re-evaluated as aspen enhancement due to aspen dominance in patchcuts (6/14/2018)
86 | Regeneration Thin | 1 | 1 | 1 | 0.55 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [5 empty] | Unit Dropped - Not enough trees (12/5/2017); re-evaluated as aspen enhancement due to aspen dominance in patchcuts (6/14/2018)
87 | Regeneration Thin within Defensible Space | 1 | 0.5 | 0.5 | 0.33 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
88 | Regeneration Thin within Defensible Space | 1 | 0.4 | 0.4 | 0.25 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
89 | Regeneration Thin | 1 | 1 | 1 | 0.52 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
90 | Regeneration Thin | 1 | 0.5 | 0.5 | 0.36 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
90a | Regeneration Thin within Defensible Space | 1 | 0.5 | 0.5 | 0.05 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
91 | Regeneration Thin within Defensible Space | 1 | 0.6 | 0.6 | 0.52 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
92 | Regeneration Thin | 1 | 0.5 | 0.5 | 0.4 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
92a | Regeneration Thin within Defensible Space | 1 | 0.5 | 0.5 | 0.02 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
93 | Regeneration Thin | 1 | 0.5 | 0.5 | 0.32 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
94 | Regeneration Thin | 1 | 1 | 1 | 0.51 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
95 | Regeneration Thin | 1 | 0.4 | 0.4 | 0.4 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
96 | Regeneration Thin | 1 | 2 | 2 | 2 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
97 | Regeneration Thin | 1 | 1 | 1 | 1.15 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
98 | Regeneration Thin | 1 | 0.3 | 0.3 | 0.3 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
99 | Regeneration Thin | 1 | 2 | 2 | 2.31 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
100 | Regeneration Thin | 1 | 0.5 | 0.5 | 0.5 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [5 empty] | Unit Dropped - Not enough trees (12/5/2017); re-evaluated as aspen enhancement due to aspen dominance in patchcuts (6/14/2018). Combined w/ unit 100a in layout
100a | Regeneration Thin within Defensible Space | 1 | 0.5 | 0 | 0 | Manual | Chip and/or pile & burn | NA | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [5 empty] | Unit Dropped - Not enough trees (12/5/2017); re-evaluated as aspen enhancement due to aspen dominance in patchcuts (6/14/2018). combined w/ unit 100 in layout
101 | Lodgepole Pine Treatment |  | 39 | 11.7 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
102 | Aspen Restoration | 4 | 11 | 11 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
103 | Lodgepole Pine Treatment | 4 | 20 | 6 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
104 | Ponderosa Pine Mixed Conifer Treatment |  | 8 | 8 |  | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn
105 | Ponderosa Pine Mixed Conifer Treatment |  | 12 | 12 |  | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn
106 | Aspen Restoration |  | 18 | 18 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
107 | Lodgepole Pine Treatment | 1 | 5 | 1.5 | 1 | Manual | Chip and/or pile & burn | 2018-07-10 | 2018-08-29 | NA | 2018-11-02 | NA |  | NA | Fix 1/50th | 2018-11-01 | In Progress | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA
GPS acres rounded except for Lodgepole Pine Treatment and Regeneration Thin Units
Phase 1 |  |  |  | 650 | 472.72
Phase 2 |  |  |  | 54 | 46.8
Phase 3 |  |  | 315.3
Phase 4 |  |  | 243.6

## All Design Criteria
Forsythe II Crosswalk
All Design Criteria
Design Criteria | Where Addressed | [5 empty] | Verified By | [12 empty] | Initials/Date | Comments
| Layout | Prior to Implementation | Statement of Work in Contract | Implementation | Burn Plan | Post Treatment | Soils / Hydrologist / Fisheries | Botanist / Noxious Weeds | Pre-Sale Forester / Contract Administrator | Silviculturist | Fuels Specialist | Burn Boss | Wildlife | PAO | Recreation | Archeologist | Lands | Engineering | Landscape Arch
All Treatment Areas
Following project implementation, at least 70% effective ground cover should be maintained within mechanical and manual treatment units to lower the risk of soil erosion. Effective ground cover includes surface rock cover, pine needle cover, and cover provided by low lying vegetation and mulch. |  |  | X | X |  | X | X | X | X
In chipped areas, chip depth shall average less than 3”. Chip depth of up to 5” may occur over small areas (not to exceed 5% of the treatment unit). Chips shall be distributed in a mosaic pattern over no more than 30% of the activity area. |  |  | X | X |  |  | X | X | X
In masticated areas, chunks shall be distributed to avoid dense accumulations that could potentially impede growth of native grasses, forbs or seedlings. |  |  | X | X |  |  | X | X | X
All treatment areas will be reviewed by a USFS Landscape Architect prior to final unit layout. Unit boundaries shall be natural edges whenever possible and prevent the appearance of uniform tree spacing and straight line unit boundaries. Straight line boundaries shall be treated by ‘feathering’ and ‘scalloping’. | X |  |  | X |  |  |  |  | X | [9 empty] | X
Minimize damage to aspen 8” DBH and larger. |  |  | X | X |  |  |  |  | X |  |  |  | X
Leave live and dead wildlife trees as individually designated by a USFS Wildlife Biologist and/or according to marking guidelines agreed to in coordination with a USFS Wildlife Biologist, Silviculturist, Fuels Planner, and prep crews. Leave trees may include trees with cavities, trees with large squirrel middens, and/or Abert’s squirrel nest trees. | X | X | X | X |  |  |  |  | X | X |  |  | X
Within treatment units where Rocky Mountain juniper occurs, leave an average of one large individual, or clump of three or more if available, Rocky Mountain Juniper per acre. | X |  | X | X |  |  |  |  | X | X |  |  | X
If a federally listed or USFS sensitive wildlife species is identified within treatment units or areas potentially impacted by proposed project activities prior to or during implementation, a USFS Wildlife Biologist will be contacted as soon as possible to ensure Forest Plan direction and Endangered Species Act requirements are met. | X | X | X | X |  |  |  |  | X |  |  |  | X
If raptor nesting activity (e.g. nesting behavior, nest sites, or fledglings) is detected within treatment units or areas potentially impacted by proposed project activities prior to or during implementation, a USFS Wildlife Biologist will be contacted as soon as possible to ensure Forest Plan direction for nesting raptor protection are met. | X | X | X | X |  |  |  |  | X |  |  |  | X
Retain a minimum of 5 of the largest available dead trees, in clumps where available, minimum 8” DBH for lodgepole and 10” for ponderosa pine and Douglas-fir, per acre, as an average across each treatment unit. Give preference to retaining ponderosa pine snags where available. Criteria for snag selection will be specified in the silviculture prescription with emphasis on retaining the largest diameter snags present. If the minimum number of snags is not available, then the largest available live, green replacement trees will be retained for future snags. | X | X | X | X |  |  |  |  | X | X |  |  | X
Retain a minimum of 5 logs and 100 linear feet per acre of existing down logs distributed randomly across each unit, with a minimum diameter of 8” for lodgepole pine and 10” for other conifer species. Do not cut live trees to meet this criterion, except where live trees will be cut according to the prescription in lodgepole pine patchcuts and clearcuts. Jackstrawed bole wood, created by treatment, 6” in diameter or greater and left in the unit must be scattered and be in contact with the ground. Individual boles of 6” or greater can be left unbucked. |  |  | X | X |  |  |  |  | X | X |  |  | X
Within flammulated owl territories: a. Thin small and medium sized trees to maintain large-open grown canopies. b. Retain live trees, 12” DBH and greater, including on ridgelines. c. In riparian areas, leave all trees with existing cavities and remove conifers less than 8” DBH except those with cavities. | X |  | X | X |  |  |  |  | X |  |  |  | X
All treatment units adjacent to existing raptor nests will be resurveyed the nesting season prior to implementation. This is to ensure that the birds have not moved their nests into an active unit. |  | X | [6 empty] | X |  |  |  | X
Buffer known roost locations for Fringed myotis bat and Townsend’s big-eared bat from treatment activities during key activity times. Prescribed burning should avoid smoke saturation of roost sites during key activity times. |  | X | X | X | X |  |  |  | X |  |  | X | X
Sensitive plant species and species of local concern locations will be determined by a USFS Botanist and designated buffers will be applied. | X |  | X | X |  |  |  | X | X
All areas potentially impacted by proposed project activities that have not been surveyed for rare plants and that contain high-quality suitable habitat for sensitive and local concern plant species will be surveyed in such habitat prior to disturbance activities. | X | [6 empty] | X | X
To minimize risk of noxious weed introduction and spread, require all equipment to be used for ground-disturbing activities for this project (not including service trucks or other vehicles that remain on roadways) to be cleaned, i.e., free of mud, dirt, plant parts, and seeds, or other debris that could contain or hold seeds, prior to entering the project area. All wheeled or tracked vehicles, including trailers, or other equipment entering constructed temporary roads shall be cleaned prior to entry to the project area. Equipment will be considered free of soil and other debris when a visual inspection does not disclose such material. Equipment shall be re-cleaned prior to transfer from a unit where noxious weeds are known to be present into a unit where noxious weeds are not known present. |  |  | X | X |  |  |  | X | X
For known weed occurrences and for any new noxious weed infestations found in or near units prior to or during implementation of vegetation treatment, implementation personnel will coordinate with USFS District Invasive Plants Coordinator to implement appropriate prevention measures, such as avoidance, treatment of weeds prior to fuels implementation, and/or additional equipment cleaning requirements, such as between infested and uninfested units. | X | X | X | X |  | X |  |  | X
Coordinate with USFS District Invasive Plants Coordinator to locate landings, staging areas, skid trails, burn piles, and other areas of severe soil disturbance to best reduce risk of spread of invasive plants. | X |  | X | X |  |  |  | X | X |  |  |  | X
Use non-agricultural mulch materials for revegetation and sediment/erosion control. Non-agricultural products include wood straw or shred and wattles made from excelsior, wood or other non-agricultural materials. |  |  | X | X |  | X |  | X | X
To avoid damage to the Boulder Gravity Line, driving across the line shall be avoided. | X |  |  | X |  |  |  |  | X | [7 empty] | X
Consultation with Denver Water Board shall occur for any project activities occurring within the FERC boundary for the Gross Reservoir Hydroelectric Project. | X | X | [14 empty] | X
There are several utility (electric, natural gas and communication) lines within the project area. Care shall be taken when working around these lines to avoid damage to them or their infrastructure. | X | X |  | X |  |  |  |  | X | [7 empty] | X
All recreation facilities (NFS roads, NFS trails, recreation sites) and infrastructure (such as gates, fences, sign kiosks, picnic tables) shall be protected from damage from all treatment activities. Any damaged facilities or infrastructure shall be repaired, replaced, or reconditioned to the level of the existing condition, or greater, to provide safe public access, as needed. Consult with Recreation Staff and/or Specialist as needed. |  |  | X | X |  |  |  |  | X | [5 empty] | X |  |  | X
High use public access portals (such as trailheads and highly traveled trail corridors) will not be used for fuels treatment project work or long term operations unless no other alternative exists. If used, safe public access on weekends will be provided. Fuels treatment work sites will be designed in a manner to allow safe public access even when occupied. Where this is not feasible, short-term forest orders closing fuels treatment areas to public access will be implemented, as needed, to ensure public safety, protect natural resources and improve effectiveness of project area objectives. Involve the Recreation Staff and/or Specialist through planning, implementation, and monitoring as needed. | X |  | X | X | X |  |  |  | X |  |  |  |  | X | X
Public notification shall occur prior to major project activities to raise public awareness. Local agency cooperators will be notified about the duration, intensity, and potential issues for the project work. |  | X |  | X | X | [8 empty] | X
Knolls (small rounded hilltops) and geologic features (rock outcrops) will be excluded from treatment to maintain aesthetic values. These features are identified as the highest point in the local vicinity that have a few trees exhibiting characteristics such as stunted growth, irregular crown shapes, and mature bark attributes. Treatment exclusions will extend down from the peak of the feature to the area where mechanical equipment can operate, approximately 40%, or the point where the vegetation transitions into a meadow dominated by grass and forbs. | X | [7 empty] | X | X |  |  |  |  | X
Mechanical Treatment Areas
No mechanical logging equipment (e.g. feller-bunchers, skidders, etc.) shall be permitted to operate within a 100 foot buffer from the edge of the water around perennial streams, intermittent streams, lakes, ponds, wetlands, fens, or wet meadows. A no mechanical treatment buffer of 328 feet (100 meters) from the edge of the water shall be established around Winiger Gulch and the unnamed southern tributary to Winiger Gulch as shown in the attached map. Activities that shall be excluded from the buffer include: • Mechanical fuels treatment operations using heavy equipment • Machine piles • Vehicle service and fueling areas • Driving tracked or wheeled machinery except along existing roads, in the southwest corner of Unit 40 and the northeast corner of Unit 74 where they overlap mapped Preble’s meadow jumping mouse habitat. | X |  | X | X |  |  | X | X | X |  |  |  | X
For ephemeral streams, equipment shall be excluded from the stream channel, except to cross at points designated by a USFS Contract or Sale Administrator(s). | X |  | X | X |  |  | X |  | X
Limit operation of heavy equipment to slopes of less than 30%. Slopes up to 40% may be considered on a site specific basis and will require evaluation by a Soils Scientist. | X |  | X | X |  |  | X |  | X | X
Slash take back will only be allowed on skid trails, in patchcut/clearcut units where it is needed to meet the coarse and fine woody debris retention criteria (see Patchcut/Clearcut Areas, 1a and 1b, in this document), or other areas designated as adversely impacted by a USFS Soil Scientist/Hydrologist/COR/Sale Administrator, for soil stabilization, and to a maximum depth of 18 inches. |  |  | X | X |  |  | X |  | X | X | X
A cultural resource inventory will be completed on all units that have been identified by a USFS Archaeologist in consultation with the SHPO. The survey and reports will be completed and sent to the SHPO prior to project implementation. Implementation will not begin until the SHPO has concurred with a determination of no historic properties affected or no historic properties adversely affected. | X | X |  |  | X |  |  |  | X | X | [5 empty] | X
Sites located during the field inventory that are evaluated as eligible for the NRHP, will have a 50 foot buffer placed around the exterior site boundary. No mechanical treatment will occur within the site boundary and the 50 foot buffer. When treatment is necessary, eligible sites and the 50 foot buffer will be hand treated for hazard trees and accumulated fuel build up by hand felling trees. Slash will either be hand piled for chipping and/or bucked up by hand, and loaded onto rubber tired vehicles to be hauled to designated burn piles for burning. No thinning, pile burning, or other slash treatments will occur within these buffers unless determined to be appropriate by a USFS Archaeologist. | X | X |  | X |  |  |  |  | X | X | [5 empty] | X
All NRHP eligible or unevaluated sites within the units proposed for mechanical treatments will be flagged on the ground for avoidance during implementation. | X | X | X | X |  |  |  |  | X | X | [5 empty] | X
Previously undiscovered sites encountered during the course of project activities will be avoided until they can be evaluated by a USFS Archaeologist. If affected properties are discovered after project activities are completed, the USFS will document any damage and consult with SHPO and Council pursuant to the procedures in 36CFR Part 800.13(b). |  |  |  | X |  |  |  |  | X | [6 empty] | X
Manual Treatment Areas
Tree cutting of conifers can occur to the edge of the stream bank for perennial, intermittent and ephemeral streams. No woody riparian vegetation (e.g. willows, alders, river birch, etc.) shall be cut. Trees shall be directionally felled away from stream channels where practicable. | X |  | X | X |  |  | X |  | X | X
Retain all existing down woody material 5” DBH or greater within and up to 100 feet of riparian areas. This applies to portions of Units 40 and 74 where they overlap Preble’s meadow jumping mouse habitat. |  |  | X | X | X |  |  |  | X | X |  |  | X
Lopped and scattered slash shall be removed from the stream channel of perennial, intermittent and ephemeral streams. |  |  | X | X |  |  | X |  | X
No tree cutting shall occur within wetlands, fens, or wet meadows. These features may not be mapped, and may only be discovered during unit layout. | X |  | X | X |  |  | X |  | X | X
Mixed Conifer Areas
Trees shall be marked as either leave trees or cut trees, whichever is most efficient, prior to any cutting. | X | [7 empty] | X | X
Recognizing that not all units may have trees greater than 14 inches DBH, and to acknowledge the value of larger trees to the public, the diameter cut limit will be adjusted based on the existing condition while retaining 10% of the existing basal area in the largest diameter trees in each unit. The maximum diameter cut limit is 14 inches DBH. | X |  | X | X |  |  |  |  | X | X
Patchcut/Clearcut Areas
Retain coarse and fine woody debris (CWD and FWD) throughout clearcut/patchcut units to maintain long term soil productivity. a. At least 8 tons/acre of CWD , with preference for large diameter material (boles) b. At least 4 tons/acre of FWD |  |  | X | X |  |  | X |  | X | X | X
Involve a USFS Wildlife Biologist during layout of patchcuts/clearcuts to determine needs for narrow areas and/or island exclusions for wildlife crossing and cover. | X | [7 empty] | X | X |  |  | X
In general, locate openings away from system trails, or social trails that will be changed to system trails, once a Decision is made on the Magnolia Trails Project. A wildlife biologist shall approve locations of patchcuts and clearcuts in the vicinity of such trails. | X | [7 empty] | X | X |  |  | X
In order to meet scenery standards within the proposed patchcut/clearcut lodgepole pine dominated units, three to five uncut islands of trees must be retained within patchcut/clearcuts greater or equal to 5 acres in size. These islands shall be at least ½ acre in size and total 25% of the appropriate patchcut/clearcut area within each unit. The acreage within the islands will not decrease the number of overall acres to be cut within a designated patch/clearcut unit. For example in unit 11 (20 acres), 30% or 6 acres of the unit could be cut utilizing a combination of patchcut/clearcuts. To equate to a one 6-acre clearcut that is treated, the boundary of the clearcut will encompass 7.5 acres to account for the 25% acre retention to be included without changing the intent of reducing the overall acreage by 30%. | X |  | X | X |  |  |  |  | X | X | [8 empty] | X
Retain all areas of mixed conifer inclusions ½ acre or less in lodgepole pine stands. If the inclusion is larger, thinning as prescribed could be implemented. An exception is cutting trees for skid trails and landings. | X | [7 empty] | X | X |  |  | X
Old Growth/Effective Habitat/Interior Forest Areas
In Management Area 3.5, exclude vegetation treatment from inventoried or discovered lodgepole pine old growth per Forest Plan standard. Exceptions may be made if the lodgepole old growth is considered non-functional at time of implementation. This determination of functionality is to be made for the stand as a whole within the treatment unit. | X |  |  | X |  |  |  |  | X | X |  |  | X
Where effective habitat occurs in treatment units, unit boundaries and/or canopy cover reduction may be modified as determined by a wildlife biologist, if needed to maintain these habitats. | X |  |  | X |  |  |  |  | X | X |  |  | X
Within mapped interior forest and within a 328 foot buffer around mapped interior forest, retain at least 40% canopy cover. Exceptions may occur based on involvement of wildlife biologist and silviculturist and use of updated USFS data. | X |  |  | X |  |  |  |  | X | X |  |  | X
Retain a minimum of 5 of the largest available dead trees, minimum 8” DBH for lodgepole and 10” for ponderosa pine and Douglas-fir, per acre, as an average across old growth retention and inventoried stands within a treatment unit. Give preference to retaining ponderosa pine snags where available. Criteria for snag selection will be specified in the silviculture prescription with emphasis on retaining the largest diameter snags present. If the minimum number of snags is not available, then the largest available live, green replacement trees will be retained for future snags. |  |  | X | X |  |  |  |  | X | X |  |  | X
Slash Piles
To the extent practicable, construct machine slash piles on landings. If machine piling is done off landings, conduct piling to leave topsoil in place and to avoid displacement of topsoil. Machinery that lifts and places material into burn piles is recommended over machinery that pushes or drags material into burn piles. |  |  | X | X |  |  | X |  | X | X | X
Hand constructed burn piles shall be located at least 50 feet from perennial streams, wetlands, fens, wet meadows, and aspen stands. For intermittent and ephemeral streams, burn piles shall be located 50 feet from the stream or outside the inner gorge, whichever is less. For Preble’s meadow jumping mouse, piles shall be located at least 100 feet from the edge of the water around Winiger Gulch and the unnamed southern tributary to Winiger Gulch. If it not practicable to locate piles sufficiently away from streams, or if doing so will violate other requirements (e.g. minimum spacing between piles, minimum distance from residual trees), do not cut the water adjacent trees, unless approved by a USFS Soil Scientist, Hydrologist, or Fish Biologist. | X |  | X | X |  |  | X | X | X | X |  |  | X
To minimize long term effects of pile burning, watershed, botany and/or implementation personnel will conduct surveys to identify if and where burn pile restoration actions are needed following pile burning activities. Any combination of the following restoration actions will be recommended if/where needed: a. Tilling/scarifying after burning to promote recovery by breaking up water repellent layers, increasing water infiltration, and mixing in organic material from areas adjacent to the pile. b. Weed treatments c. Seeding d. Covering with litter, duff and/or slash |  |  |  |  | X | X | X | X
Burn piles should be located out of sight of major viewpoints as designated by a USFS Landscape Architect whenever possible within the constraints of the contract. |  | X | X | X |  |  |  |  | X | [9 empty] | X
In treatment units where slash is piled by hand, leave an average of 2 piles per acre for wildlife habitat, including any piles remaining from previous vegetation treatment, distributed randomly throughout the unit. |  |  |  |  | X |  |  |  | X |  |  | X | X
Minimum pile size, hand or machine created, shall be no less than 6 feet high by 6 feet wide. |  |  | X | X |  |  |  |  | X |  | X
Consult USFS Fuels Specialist during contract preparation for current maximum pile size and pile separation requirements as regulated by the Colorado Air Pollution Control Division. |  | X | [6 empty] | X |  | X | X
Piles shall be constructed in a manner to minimize large air spaces and dirt within the piles. Piles shall not have material extending more than 4 feet in any direction beyond the pile perimeter and a minimum of 4 feet of separation from pile perimeter to surrounding down woody material to reduce unwanted fire spread. |  |  | X | X |  |  |  |  | X |  | X | X
Construct a minimum of a 6 foot wide control line, down to bare mineral soil, around each machine pile to create separation between piled material and surrounding slash mat. If piles are grouped, a single control line may be placed around the entire group rather than around individual piles. The scraped material must be moved outward to avoid a berm adjacent to the piles’ edge. |  |  | X | X |  |  |  |  | X |  | X | X
In machine units, reasonably gather and place activity slash material, 1” to 6” diameter, into piles. If more than 50% of a treatment unit has continuous slash depth greater than 6” after initial treatment, additional piling will be required. |  |  | X | X |  |  |  |  | X |  | X
In manual units, pile sound, existing and/or created slash material, 1” to 6” diameter and 2 feet or longer. Alternatively, any slash that must be moved more than 50 feet to meet minimum required pile size may be lopped and scattered to a maximum depth of 18”. Lopped and scattered material is expected to be a rare occurrence and most likely occur in very open grown areas where a few trees are required to be cut to meet spacing specifications, but not enough trees are cut to produce enough slash to create a minimum sized pile. |  |  | X | X |  |  |  |  | X |  | X
Locate machine piles a minimum of 150 feet and hand piles a minimum of 50 feet from any infrastructure or private property boundary. |  |  | X | X |  |  |  |  | X |  | X | X
Broadcast Burning
Limit total unrecovered burned area within the project area to no more than 340 acres. |  |  |  | X | X |  | X |  |  |  |  | X
Design and implement prescribed fire for low soil burn severity effects and rapid recovery of ground cover. Soil burn severity classes are defined in the Field Guide for Mapping Soil Burn Severity (http://www.fs.fed.us/rm/pubs/rmrs_gtr243.pdf). |  |  |  | X | X |  | X |  |  |  |  | X
Rehabilitate constructed fire lines by installing water bars, raking topsoil back over the line, covering with slash or other mulch materials; and seeding, if recommended by a USFS Botanist. |  |  |  |  | X | X | X | X |  |  |  | X
A 300 foot buffer shall be established around Winiger Gulch and the unnamed southern tributary to Winiger Gulch as shown in the attached map. No active ignition shall occur within the buffer. Fire will be allowed to back down into riparian areas and streamside zones. If needed to accomplish burn objectives or to provide for safety, establishment of control features (e.g. fire lines) or active ignition may occur within the buffer following consultation and agreement with a USFS Fish Biologist, Soil Scientist or Hydrologist. |  |  |  | X | X |  | X |  |  |  |  | X
Conduct burning operations so that no more than 10% of either stream bank area within riparian zones burns with high intensity (i.e. top kill of willow and/or aspen). Actively suppress fire if this 10% threshold is exceeded. |  |  |  | X | X | [6 empty] | X
No active ignition shall occur within 25 feet of ephemeral streams. |  |  |  | X | X |  | X |  |  |  |  | X
In prescribed burn Units 38 and 44, choose individuals or clumps of three or more, if available, Rocky Mountain juniper to leave that are not ladder fuels for other conifers 12”+ DBH. Leave trees should be at least 300 feet away from property boundaries and prescribed burn containment lines. |  |  |  | X | X |  |  |  | X | X |  | X | X
Prior to prescribed burning in Units 38 and 44 within inventoried old growth, old growth retention, and identified old growth development areas, remove ladder fuels from around trees 12” DBH and larger to minimize fire moving into crowns of these larger trees. Where feasible, such as near firelines during mopup, moisten coarse woody material within root zones of trees 12” DBH and larger, to minimize root damage from smoldering material. |  | X |  | X | X |  |  |  | X | X |  | X | X
Prior to prescribed burning in Units 38 and 44, scratch fireline around and/or use other techniques to minimize fire impacts to at least 5 logs per acre totaling at least 100 linear feet. These logs should have a minimum diameter of ten inches if available, or largest down logs available. |  | X |  | X | X | [6 empty] | X | X
A cultural resource inventory will be completed on all areas within prescribed burn units that have been identified by a USFS Project Archaeologist in consultation with the SHPO. This inventory may be completed after the NEPA decision has been made but prior to burn implementation. |  | X | [9 empty] | X |  |  |  | X
All NRHP eligible or unevaluated sites located within prescribed burn units will be marked on the ground by the Project Archaeologist. A USFS Project Archaeologist and Fire Staff will design protection measures to remove the sites from the burn’s Area of Potential Effects. These protection measures will take into consideration the site type, environmental setting, and anticipated burn conditions. These protections may include, but are not limited to: fuel breaks, no treatment buffers, wrapping, foaming, wetting, black line, fire line (machine or hand dug), and raking. |  | X |  | X | X | [6 empty] | X |  |  |  | X
All potentially ground-disturbing fire lines, staging areas, helispots, and all road improvement, construction or deconstruction, or designated ATV or vehicle routes/ways will be intensively (Class III) surveyed for cultural resources prior to project implementation; any NRHP-eligible cultural resources will be avoided by project design. |  | X |  | X | X | [6 empty] | X |  |  |  | X
Timing Restrictions
Avoid treatment operations from May 1 through August 10 in flammulated owl territories. Avoidance areas will be determined by a USFS Wildlife Biologist based on survey results, flammulated owl territory size, topography, and vegetation. Prescribed burning operations may be conducted if determined to be appropriate by a USFS Wildlife Biologist. This applies to most units in the Winiger Ridge and South Winiger areas, and may apply to other areas if appropriate based on survey results. |  |  | X | X | X |  |  |  | X |  |  |  | X
Raptor nest areas, including species-specific buffers, will generally have no treatment activity from March 1 through September 15, depending on species, or until determined unoccupied by the wildlife biologist. Access through buffers during this period will be assessed by a USFS Wildlife Biologist. a. If known nests become unoccupied, additional surveys will be conducted during the breeding season prior to any project activity. The extent and timing of surveys will be determined by a USFS Wildlife Biologist. b. Units with suitable nest habitat will also be resurveyed for new nest locations prior to implementation. If a new active nest is detected during surveys or becomes known by other means, appropriate mitigations will be implemented. c. For northern goshawk nests including alternate nest sites, exclude treatment in up to a 30-acre area containing the nest tree. Site-specific exclusion areas will be determined by a USFS Wildlife Biologist based on topography, vegetation and other factors. Outside of the breeding season, generally from September 16 through February 28, limited thinning may be allowed within this area if determined necessary to help reduce the risk of losing the nest site to wildfire. A USFS Wildlife Biologist will help design and approve treatment. | X | X | X | X | X |  |  |  | X |  |  |  | X
Unless a site-specific exception is determined to be appropriate by a USFS Wildlife Biologist, avoid treatment from December 1 through March 30 in elk severe winter range and winter concentration areas. These areas are based on the most current available mapping data from Colorado Parks and Wildlife. |  |  | X | X | X |  |  |  | X |  |  |  | X
Project operations will not be conducted on Memorial Day, 4th of July and Labor Day holiday weekends and on Sundays. Operating times for heavy equipment and chainsaws shall be limited to the hours of 7 a.m. to 7 p.m. |  |  | X | X |  |  |  |  | X | [5 empty] | X
Piles outside the 100 foot riparian buffer but within 328 feet of the stream channel may only be burned from November 1 through April 30 during Preble’s meadow jumping mouse hibernation. This applies to Units 40 and 74. |  |  |  |  | X | [6 empty] | X | X
Roads/Skid Trails/Temp Roads/Landings/Equipment Use
Temporary roads, skid trails, landing areas, and equipment use in mechanical treatment units shall be subject to operating equipment restrictions to protect soil and water. Operate heavy equipment only when soil moisture in the upper 6 inches is below the plastic limit (a ball can be formed in the fist that holds together on gentle tossing or shaking) OR protected by at least one foot of packed snow or 2 inches of frozen soil. This may mean temporary restriction on equipment operation and travel within the treatment area in periods of heavy rains and snow or when soils are wet. |  |  |  | X |  |  | X |  | X | [8 empty] | X
The USFS shall approve locations of skid trails and landings prior to treatment. Re-use existing skid trails as much as practicable to minimize new disturbance. Within mapped effective habitat, a USFS Wildlife Biologist will approve locations of skid trails and landings. |  |  | X | X |  |  |  |  | X |  |  |  | X |  | X
All temporary road construction, including skid trails, shall be obliterated within one year of completion of use, including pile burning. Project implementation, watershed, soil, and engineering personnel shall cooperate to determine appropriate obliteration methods. a. Temporary road surfaces, including skid trails and landings, shall be decompacted along the entire road/skid trail length or landing area unless waived by Soil Scientist. Roads that were constructed with cut and fill shall be partially or fully recontoured or pitted. Roads that were constructed on the natural ground contour shall be pitted, subsoiled, or ripped. • Partial recontouring of the road prisms shall be utilized in areas where it is not feasible or beneficial to disturb soils previously unaffected by construction operations to stabilize a decommissioned temporary road. Factors such as steep slopes, large amounts of rock, or vegetation may impact a decision to utilize partial recontouring. Partial recontouring shall use available fill material from original construction. Fills shall be returned to, and compacted into, the cut removal area. No further ground disturbance involving cutting material shall occur. Handle soil to ensure that minimal segregation of materials occurs. Compaction may be by machine track or bucket. The recontoured surface shall be outsloped a minimum of 5% for the entire road prism width and no berms shall remain. Finished grades shall minimize drainage following the contour of the road, where necessary grade dips shall be installed along the grade to direct drainage off the disturbed area. Where high cut slopes are present, continue pulling up fill material and backfilling cut removal areas until no cut slope remains greater than 1:1 H:V in slope and two feet in height. • Full recontouring of the road prisms shall be utilized in decommissioning temporary road segments where it is both feasible and advantageous to disturb soil previously unaffected by construction operations to completely recontour the road. Full recontouring shall include pull up of all fill material and place/compact into the cut removal area. Very little disturbance of the natural ground under the fill shall occur. The final slope area, over the entire width of the road prism, shall reproduce the pre-road natural slope. It shall blend in with the surrounding slope and no berms or windrows of any material shall remain. | [5 empty] | X | X | X | X | [5 empty] | X |  |  | X | X
b. Where applicable, remove all temporary stream crossings and restore stream bed and banks. c. Restore natural drainage patterns across the road template. d. Provide effective closure at junctions with open roads and NFS trails to prevent unauthorized use. Effective closure techniques may include recontouring or pitting for site distance, fencing, gates, berms, barrier rocks of various sizes (median size of 2.5 ft. x 2.5 ft. x 2.5 ft. [1 ton], grouped in natural arrangements and 1/3-1/2 buried), plantings, and/or felled trees. e. Scatter slash on restored disturbance. f. Restore ground cover using native seed or plants, methods and timing, and soil amendments as practicable to meet revegetation objectives and in consultation with a USFS Botany Representative. Use government furnished seed when available.
Vegetation treatment implementation and related contracting will incorporate use of existing and/or previously used areas as much as possible for fuels treatment operations, in order to reduce the amount of new disturbance which usually leads to new “social” routes being created. Any non-system roads which are used for access to fuels treatment units shall be considered to be temporary roads and shall be obliterated following the design criteria for temporary roads. | X |  |  | X |  | X |  |  | X | [5 empty] | X
Where topsoil depth exceeds 2”, topsoil shall be salvaged and stockpiled from all areas to be disturbed by construction of temporary roads and road improvements and shall be incorporated into the reclamation. |  |  | X | X |  | X | X |  | X
Temporary road construction shall be kept to the minimum construction possible to accommodate intended use and shall meet the following guideline. a. Roads shall not follow fall line of the land but shall traverse contours to minimize slopes. Generally, slopes of 10 percent or less shall be maintained, however reaches of 200 feet or less may be up to 14 percent in slope. b. Road alignment shall be selected to minimize cuts and fills to 2-foot maximum. c. Road widths shall be the minimum required for the equipment and shall not exceed 15 feet. d. Roads shall be outsloped where possible and rolling dips shall be constructed instead of ditches and culverts, wherever practicable, as necessary to control sediment and erosion. Drainage features shall not drain directly into streams. Best Management Practices shall be employed at the termination of drainage features to protect vegetation from sedimentation. |  |  | X | X |  |  |  |  | X | [8 empty] | X
Construction of temporary roads and road improvements shall to the extent possible minimize ground disturbance, avoid crossings of drainages, provide buffers to drainages and sensitive areas, avoid steep slopes, avoid wet areas and swale bottoms, avoid unstable slopes, and shall minimize erosion potential and sedimentation of water ways. |  |  | X | X |  |  | X |  | X | [8 empty] | X
If material will be imported for road base or other uses, developed borrow sources or pit-run material sources will be inspected for weeds, weed parts or weed seeds by either a Forest Service employee or other party approved by the Forest Service. Aggregate base or riprap sourced from commercial pits does not need to be inspected. |  |  | X | X |  |  |  | X | X
Planning, construction and maintenance of temporary roads shall include sediment and erosion controls as necessary to prevent resource damage. Such controls are to be maintained and supplemented as necessary through the life of the project. |  |  | X | X |  |  | X | X | X | [8 empty] | X
Prior to the construction on NFS land of any egress route from Big Springs subdivision, the Forest shall approve locations, plans, best management practices, storm water management plans, and any other plans necessary to protect NFS lands and resources. Resource protection measures shall be installed and maintained during construction and for a sufficient time after construction until the site has stabilized. | X | X |  | X |  |  | X |  | X | [7 empty] | X | X
System roads shall not be used during winter and wet periods when there is a reduction in the ability of the road or road structure to support traffic, provide drainage, or provide safe transportation. Examples of reduction in the support value or safety of the roadway include, but are not limited to, soil, mud, debris, or oversized rocks incorporated into the roadway that affect drainage, normal maintenance activities, or the strength of the surface structure; intermixing of slash or subgrade soil with aggregate base; severe alteration of drainage that leads to surface aggregate loss, changes in character of ditches or drainage structures, or concentration of water that harms streams or water sources; accelerated breakdown of asphalt surfaces. If removal of snow from system roads for winter operations is allowed, provide adequate maintenance to maintain the road surface structure, drainage of the roadway, and safe passage for vehicles. Snow storage areas shall be approved by the USFS. Avoid riparian areas, wetlands or streams for snow storage to the extent possible. Space, construct, and maintain drainage holes in the dike of snow or berm caused by snow removal operations. Place drain holes to obtain surface drainage without discharging on erodible fills. Perform maintenance work in a manner to preserve and protect roads and appurtenances, and prevent erosion damage to streams and other Forest values. Any type of equipment to remove snow may be utilized provided: a. The equipment is of the size and type commonly used to remove snow and will not cause damage to the road surface or structure. b. The use of plows or dozers to remove snow requires written approval by the USFS. Equip plows or dozers with shoes or runners to keep the dozer blade a minimum of 2 inches above the road surface. |  |  | X | X |  |  | X |  | X | [8 empty] | X
Existing road conditions shall be assessed prior to implementation for all roads to be used for the project including County and private roads used to access National Forest lands. Roads shall be maintained in their existing condition through-out the project, if any widening or other improvements are required for the project these improvements shall be assessed at the completion of the project to determine if they are acceptable or need to be removed. |  | X | X | X |  | X |  |  | X | [8 empty] | X
When the work is complete the existing roads shall be inventoried to ensure drainage is operational and road surface is intact. | [5 empty] | X |  |  | X | [8 empty] | X
Unless the condition of an existing road is suitable for truck and trailer traffic, mechanized equipment shall be ‘walked’ (travel under its own power as opposed to transported on a trailer) into any units where mechanical treatments is planned. |  |  | X | X |  |  |  |  | X | [8 empty] | X
Coordinate all work and traffic that impacts County roads, including hauling, with the County ahead of the work commencing. Obtain County permits as necessary. |  | X |  | X |  |  |  |  | X |  |  |  |  | X |  |  |  | X
Coordinate with road users, who will be impacted by the work, obtain access as necessary and contact information for any temporary closures or other coordination. |  | X |  | X |  |  |  |  | X |  |  |  |  | X
All roads impacted by project activities shall have warning signs and traffic control as follows: a. In accordance with the “Manual of Uniform Traffic Control Devices.” b. Maintained for through traffic during felling, slash treatment, and/or removal operations. c. Left in an operational condition that will adequately accommodate traffic at the end of each work day. d. Have barricades erected and/or proper signs placed at any traffic hazards in or adjacent to the road at the end of each workday. e. All felled trees shall be decked or removed and slash piled or removed from the bladed, mowed, or brushed road corridor each day. |  |  | X | X |  |  |  |  | X | [8 empty] | X
Linear woody material designated to remain from roadway clearing activities shall be placed outside the clearing limits in close contact with, and perpendicular to, the slope. All other available organic and inorganic debris shall be scattered evenly outside of the clearing limits. |  |  | X | X |  | X |  |  | X | [8 empty] | X | X
Roads which have been authorized for private uses should remain available to those uses to the greatest extent possible. Any deterioration of the road should be repaired to a similar or better condition than before project activities occurred. |  | X | X | X |  | X |  |  | X | [7 empty] | X | X
Treatment units that already have off-road impacts and/or the potential for new and increased off-road vehicular use impacts are generally in areas that have a moderate or low slope angle (35% or less), and enough terrain to use the vehicle (four-wheel drive or all-terrain vehicles included). These areas will be protected from further encroachment of motorized vehicles by creating a buffer zone of no treatment or modification of treatment between the road, open for motorized travel, and the treatment area by installing fencing or other barriers made from natural materials (rock or wood). Buffer zones should be wide enough (minimum of 100 feet from edge of road) to discourage attempts at creating new routes. These areas will be identified with input from recreation staff and unit layout personnel prior to final unit boundary designation. | X |  |  | X |  | X |  |  | X | X |  |  |  |  | X
NRHP eligible sites located during the field inventory will have a 50 foot buffer established around the exterior boundary of the site. No construction activities will take place within the site and the 50 foot buffer area. | X |  |  | X |  |  |  |  | X | [6 empty] | X
All potentially ground-disturbing activities proposed for staging areas, road improvement, construction, or obliteration outside of planned treatment units will be intensively surveyed for cultural resources prior to project implementation. Any NRHP-eligible cultural resources will be avoided by project design. |  | X |  | X |  |  |  |  | X | [6 empty] | X
Consultation with Native American tribes must be completed prior to the closure of roads to ensure that access to areas of cultural importance is not inadvertently removed. | [5 empty] | X |  |  | X | [6 empty] | X |  | X

## Phase 1 Units
FORSYTHE II IMPLEMENTATION PHASE 1
Unit Number | Vegetation Treatment | Treatment Method | Slash Treatment | EA Final Unit Acres | Lpp PC/CC Treatable Acres | Mixed Conifer Acres | Aspen Acres | Meadow Acres | Regen. Acres | Est. Total Treatment Acres | Total GPS Acres | Comments
1 | Lodgepole Pine Treatment | Manual | Chip and/or pile & burn | 15 | 4.5 | 1.5 | 3 |  |  | 9 | 6.3
2 | Lodgepole Pine Treatment | Manual | Chip and/or pile & burn | 49 | 14.7 |  |  |  |  | 14.7 | x | Removed from Phase II Mechanical to Phase 1 Manual 6/14/2018
3 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 31 | 9.3 |  |  |  |  | 9.3 | 10.9 | Removed from Phase II Mechanical to Phase 1 Manual 8/20/2018
4 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 64 | 19.2 |  |  |  |  | 19.2 | 11.6 | Removed from Phase II Mechanical to Phase 1 Manual 8/20/2018
5 | Aspen Restoration | Manual | Chip and/or pile & burn | 17 |  |  | 17 |  |  | 17 | 9
7 | Aspen Restoration | Manual | Chip and/or pile & burn | 9 |  |  | 9 |  |  | 9 | 3
8 | Aspen Restoration | Manual | Chip and/or pile & burn | 7 |  |  | 7 |  |  | 7 | 5
39 | Douglas-fir Mixed Conifer Treatment | Manual | Northern portion - Lop/Scatter and Prescribed Broadcast Burn; Southern portion Chip and/or pile & burn | 59 |  | 44 | 15 |  |  | 59 | 36 | During layout, the Forester recommended treating unit manually instead of mechanically 6/28/2018
40 | Douglas-fir Mixed Conifer Treatment | Manual | Lop/Scatter and Prescribed Broadcast Burn | 106 |  | 106 |  |  |  | 106 | 90
41 | Meadow/Shrubland Restoration | Manual | Lop/Scatter and Prescribed Broadcast Burn | 29 |  |  |  | 29 |  | 29 | 24
42 | Lodgepole Pine Treatment | Manual | Chip and/or pile & burn | 19 | 5.7 | 5 | 1 |  |  | 11.7 | 5.6 | During layout, the Forester recommended treating unit manually instead of mechanically 6/28/2018
45 | Douglas-fir Mixed Conifer Treatment | Manual | Lop/Scatter and Prescribed Broadcast Burn | 131 |  | 116 | 15 |  |  | 131 | 118 | Removed acres from middle southern portion of unit from Phase 2 Mechanical to Phase 1 Manual 6/19/2018. Slash Tx is lop and scatter for Rx burn. During layout, the Forester recommended treating unit manually instead of mechanically 6/28/2018
46 | Ponderosa Pine Mixed Conifer Treatment | Manual | Lop/Scatter and Prescribed Broadcast Burn | 12 |  | 12 |  |  |  | 12 | 5
50 | Ponderosa Pine Mixed Conifer Treatment | Manual | Chip and/or pile & burn | 7 |  | 7 |  |  |  | 7 | 7
51 | Ponderosa Pine Mixed Conifer Treatment | Manual | Chip and/or pile & burn | 89 |  | 89 |  |  |  | 89 | 79
63 | Ponderosa Pine Mixed Conifer Treatment | Manual | Chip and/or pile & burn | 5 |  | 5 |  |  |  | 5 | 2
74 | 2-Staged Mixed Conifer Treatment | Manual | Chip and/or pile & burn | 44 |  | 44 |  |  |  | 44 | 41
75 | Lodgepole Pine Treatment | Manual | Chip and/or pile & burn | 14 | 4.2 |  |  |  |  | 4.2 | 2.5 | Removed from Phase II Mechanical to Phase 1 Manual 6/14/2018
76 | Lodgepole Pine Treatment | Manual | Chip and/or pile & burn | 12 | 3.6 |  |  |  |  | 3.6 | 3.4 | Removed from Phase II Mechanical to Phase 1 Manual 6/14/2018
82 | Regeneration Thin | Manual | Chip and/or pile & burn | 1 |  |  |  |  | 1.2487 | 1.2487 | 0.9
83 | Regeneration Thin | Manual | Chip and/or pile & burn | 0.4 |  |  |  |  | 0.36095 | 0.36095 | 0.4
84 | Regeneration Thin within Defensible Space | Manual | Chip and/or pile & burn | 0.3 |  |  |  |  | 0.28 | 0.28 | 0.3
85 | Regeneration Thin (changed to Aspen Restoration) | Manual | Chip and/or pile & burn | 0.63 |  |  | 0.6 |  |  | 0.6 | 0.6 | Unit Dropped - Not enough trees (12/5/2017); re-evaluated as aspen enhancement due to aspen dominance in patchcuts (6/14/2018)
86 | Regeneration Thin (changed to Aspen Restoration) | Manual | Chip and/or pile & burn | 0.55 |  |  | 0.6 |  |  | 0.6 | 0.6 | Unit Dropped - Not enough trees (12/5/2017); re-evaluated as aspen enhancement due to aspen dominance in patchcuts (6/14/2018)
87 | Regeneration Thin within Defensible Space | Manual | Chip and/or pile & burn | 0.5 |  |  |  |  | 0.46 | 0.46 | 0.3
88 | Regeneration Thin within Defensible Space | Manual | Chip and/or pile & burn | 0.4 |  |  |  |  | 0.36 | 0.36 | 0.3
89 | Regeneration Thin | Manual | Chip and/or pile & burn | 1 |  |  |  |  | 0.7676 | 0.7676 | 0.5
90 | Regeneration Thin | Manual | Chip and/or pile & burn | 0.5 |  |  |  |  | 0.53432 | 0.53432 | 0.5
90a | Regeneration Thin | Manual | Chip and/or pile & burn | 0.5 |  |  |  |  | 0.5 | 0.5 | 0.5
91 | Regeneration Thin within Defensible Space | Manual | Chip and/or pile & burn | 0.6 |  |  |  |  | 0.57 | 0.57 | 0.6
92 | Regeneration Thin | Manual | Chip and/or pile & burn | 0.5 |  |  |  |  | 0.51786 | 0.51786 | 0.5
92a | Regeneration Thin | Manual | Chip and/or pile & burn | 0.5 |  |  |  |  | 0.51786 | 0.51786 | 0.5
93 | Regeneration Thin | Manual | Chip and/or pile & burn | 0.5 |  |  |  |  | 0.47872 | 0.47872 | 0.5
94 | Regeneration Thin | Manual | Chip and/or pile & burn | 1 |  |  |  |  | 0.5302 | 0.5302 | 0.5
95 | Regeneration Thin | Manual | Chip and/or pile & burn | 0.4 |  |  |  |  | 0.43296 | 0.43296 | 0.4
96 | Regeneration Thin | Manual | Chip and/or pile & burn | 2 |  |  |  |  | 2.0021 | 2.0021 | 2
97 | Regeneration Thin | Manual | Chip and/or pile & burn | 1 |  |  |  |  | 1.4171 | 1.4171 | 1.4
98 | Regeneration Thin | Manual | Chip and/or pile & burn | 0.3 |  |  |  |  | 0.32232 | 0.32232 | 0.3
99 | Regeneration Thin | Manual | Chip and/or pile & burn | 2 |  |  |  |  | 2.4743 | 2.4743 | 2.5
100 | Regeneration Thin (changed to Aspen Restoration) | Manual | Chip and/or pile & burn | 0.53 |  | 0.53 |  |  |  | 0.53 | 0.5 | Unit Dropped - Not enough trees (12/5/2017); re-evaluated as aspen enhancement due to aspen dominance in patchcuts (6/14/2018)
100a | Regeneration Thin (changed to Aspen Restoration) | Manual | Chip and/or pile & burn | [6 empty] | 0 | 0.5 | Unit Dropped - Not enough trees (12/5/2017); re-evaluated as aspen enhancement due to aspen dominance in patchcuts (6/14/2018)
107 | Lodgepole Pine Treatment | Manual | Chip and/or pile & burn | 5 | 1.4 |  | 2 |  |  | 3.4 | 1
Total |  |  |  | 739.11 | 62.6 | 430.03 | 70.2 | 29 | 13.7751 | 605.6051 | 475.4
* Includes acres in both units and D-space buffer

## Phase 2 Units
FORSYTHE II IMPLEMENTATION PHASE 2
Unit Number | Vegetation Treatment | Treatment Method | Slash Treatment | EA Final Unit Acres | Calc. Acres | Lpp PC/CC Treatable Acres | Mixed Conifer Acres | Aspen Acres | Meadow Acres | Regen. Acres | Est. Total Treatment Acres | Total GPS Acres | Est. CCF | Total CCF | Comments
24 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 16 | 16.4 | 4.9 |  |  |  |  | 4.9 | x | 25
26 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 122 | 36.6 | 36.6 |  |  |  |  | 36.6 | 16 | 183
27 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 55 | 16.5 | 16.5 |  |  |  |  | 16.5 | 7 | 83
28 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 109 | 32.7 | 32.7 |  |  |  |  | 32.7 | 25 | 164
Total |  |  |  | 302 | 102.2 | 90.7 | 0 | 0 | 0 | 0 | 90.7 | 48 | 455

## Phase 3 Units
FORSYTHE II IMPLEMENTATION PHASE 3
Unit Number | Vegetation Treatment | Treatment Method | Slash Treatment | EA Final Unit Acres | Lpp PC/CC Treatable Acres | Mixed Conifer Acres | Aspen Acres | Meadow Acres | Regen. Acres | Est. Total Treatment Acres | Total GPS Acres | Comments
30 | Lodgepole Pine | Manual | Chip and/or pile & burn | 14 | 4.2
31 | Lodgepole Pine | Manual | Chip and/or pile & burn | 73 | 21.9
43 | Douglas-fir Mixed Conifer Treatment | Manual | Chip and/or pile & burn | 42 |  | 39 | 3 |  |  | 42 |  | During layout, the Forester recommended treating unit manually instead of mechanically 6/28/2018
47 | Douglas-fir Mixed Conifer Treatment | Manual | Chip and/or pile & burn | 20 |  | 20 |  |  |  | 20 |  | Need to contact Pineview Subdivision about letter to treat to the boundary. Buffer acres would need to be included if agreeable.
48 | Ponderosa Pine Mixed Conifer Treatment | Manual | Chip and/or pile & burn | 75 |  | 68 | 7 |  |  | 75 |  | Need to contact Pineview Subdivision about letter to treat to the boundary. Buffer acres would need to be included if agreeable. Recon - maybe an inclusion of lpp in northern portion. During layout, the Forester recommended treating unit manually instead of mechanically 6/28/2018
49 | Ponderosa Pine Mixed Conifer Treatment | Manual | Chip and/or pile & burn | 47 |  | 47 |  |  |  | 47 |  | During layout, the Forester recommended treating unit manually instead of mechanically 6/28/2018
68 | Douglas-fir Mixed Conifer Treatment | Manual | Chip and/or pile & burn | 10 |  | 10 |  |  |  | 10 |  | During layout, the Forester recommended treating unit manually instead of mechanically 6/28/2018
73 | Ponderosa Pine Mixed Conifer Treatment | Manual | Chip and/or pile & burn | 76 |  | 76 |  |  |  | 76 |  | During layout, the Forester recommended treating unit manually instead of mechanically 6/28/2018
|  |  | Totals | 357 | 26.1 | 260 | 10 | 0 | 0 | 270 | 0
* Includes acres in both units and D-space buffer

## Phase 4 Units
FORSYTHE II IMPLEMENTATION PHASE 4
Unit Number | Vegetation Treatment | Treatment Method | Slash Treatment | EA Final Unit Acres | Lpp PC/CC Treatable Acres | Mixed Conifer Acres | Aspen Acres | Meadow Acres | Regen. Acres | Est. Total Treatment Acres | Total GPS Acres | Comments
9 | Douglas-fir Mixed Conifer Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 156 |  | 156
10 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 8.4 | 8.4
11 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 6 | 6
12 | Douglas-fir Mixed Conifer Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 7 |  | 7
29 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 164 | 49.2
102 | Aspen Restoration | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 11 |  |  | 11
103 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 20 | 6
|  |  | Totals | 372.4 | 69.6 | 163 | 11 | 0 | 0 | 0 | 0

## Phase 1 Design Criteria
Forsythe II Crosswalk
Phase 1 Design Criteria
Design Criteria | Where Addressed | [5 empty] | Verified By | [12 empty] | Initials/Date | Comments
| Layout | Prior to Implementation | Statement of Work in Contract | Implementation | Burn Plan | Post Treatment | Soils / Hydrologist / Fisheries | Botanist / Noxious Weeds | Pre-Sale Forester / Contract Administrator | Silviculturist | Fuels Specialist | Burn Boss | Wildlife | PAO | Recreation | Archeologist | Lands | Engineering | Landscape Arch
All Treatment Areas
Following project implementation, at least 70% effective ground cover should be maintained within mechanical and manual treatment units to lower the risk of soil erosion. Effective ground cover includes surface rock cover, pine needle cover, and cover provided by low lying vegetation and mulch. |  |  | X | X |  | X | X | X | X
In chipped areas, chip depth shall average less than 3”. Chip depth of up to 5” may occur over small areas (not to exceed 5% of the treatment unit). Chips shall be distributed in a mosaic pattern over no more than 30% of the activity area. |  |  | X | X |  |  | X | X | X
All treatment areas will be reviewed by a USFS Landscape Architect prior to final unit layout. Unit boundaries shall be natural edges whenever possible and prevent the appearance of uniform tree spacing and straight line unit boundaries. Straight line boundaries shall be treated by ‘feathering’ and ‘scalloping’. | X |  |  | X |  |  |  |  | X | [9 empty] | X
Minimize damage to aspen 8” DBH and larger. |  |  | X | X |  |  |  |  | X |  |  |  | X
Leave live and dead wildlife trees as individually designated by a USFS Wildlife Biologist and/or according to marking guidelines agreed to in coordination with a USFS Wildlife Biologist, Silviculturist, Fuels Planner, and prep crews. Leave trees may include trees with cavities, trees with large squirrel middens, and/or Abert’s squirrel nest trees. | X | X | X | X |  |  |  |  | X | X |  |  | X
Within treatment units where Rocky Mountain juniper occurs, leave an average of one large individual, or clump of three or more if available, Rocky Mountain Juniper per acre. | X |  | X | X |  |  |  |  | X | X |  |  | X
If a federally listed or USFS sensitive wildlife species is identified within treatment units or areas potentially impacted by proposed project activities prior to or during implementation, a USFS Wildlife Biologist will be contacted as soon as possible to ensure Forest Plan direction and Endangered Species Act requirements are met. | X | X | X | X |  |  |  |  | X |  |  |  | X
If raptor nesting activity (e.g. nesting behavior, nest sites, or fledglings) is detected within treatment units or areas potentially impacted by proposed project activities prior to or during implementation, a USFS Wildlife Biologist will be contacted as soon as possible to ensure Forest Plan direction for nesting raptor protection are met. | X | X | X | X |  |  |  |  | X |  |  |  | X
Retain a minimum of 5 of the largest available dead trees, in clumps where available, minimum 8” DBH for lodgepole and 10” for ponderosa pine and Douglas-fir, per acre, as an average across each treatment unit. Give preference to retaining ponderosa pine snags where available. Criteria for snag selection will be specified in the silviculture prescription with emphasis on retaining the largest diameter snags present. If the minimum number of snags is not available, then the largest available live, green replacement trees will be retained for future snags. | X | X | X | X |  |  |  |  | X | X |  |  | X
Retain a minimum of 5 logs and 100 linear feet per acre of existing down logs distributed randomly across each unit, with a minimum diameter of 8” for lodgepole pine and 10” for other conifer species. Do not cut live trees to meet this criterion, except where live trees will be cut according to the prescription in lodgepole pine patchcuts and clearcuts. Jackstrawed bole wood, created by treatment, 6” in diameter or greater and left in the unit must be scattered and be in contact with the ground. Individual boles of 6” or greater can be left unbucked. |  |  | X | X |  |  |  |  | X | X |  |  | X
Within flammulated owl territories: a. Thin small and medium sized trees to maintain large-open grown canopies. b. Retain live trees, 12” DBH and greater, including on ridgelines. c. In riparian areas, leave all trees with existing cavities and remove conifers less than 8” DBH except those with cavities. | X |  | X | X |  |  |  |  | X |  |  |  | X
All treatment units adjacent to existing raptor nests will be resurveyed the nesting season prior to implementation. This is to ensure that the birds have not moved their nests into an active unit. |  | X | [6 empty] | X |  |  |  | X
Buffer known roost locations for Fringed myotis bat and Townsend’s big-eared bat from treatment activities during key activity times. Prescribed burning should avoid smoke saturation of roost sites during key activity times. |  | X | X | X | X |  |  |  | X |  |  | X | X
Sensitive plant species and species of local concern locations will be determined by a USFS Botanist and designated buffers will be applied. | X |  | X | X |  |  |  | X | X
All areas potentially impacted by proposed project activities that have not been surveyed for rare plants and that contain high-quality suitable habitat for sensitive and local concern plant species will be surveyed in such habitat prior to disturbance activities. | X | [6 empty] | X | X
For known weed occurrences and for any new noxious weed infestations found in or near units prior to or during implementation of vegetation treatment, implementation personnel will coordinate with USFS District Invasive Plants Coordinator to implement appropriate prevention measures, such as avoidance, treatment of weeds prior to fuels implementation, and/or additional equipment cleaning requirements, such as between infested and uninfested units. | X | X | X | X |  | X |  | X | X
Coordinate with USFS District Invasive Plants Coordinator to locate landings, staging areas, skid trails, burn piles, and other areas of severe soil disturbance to best reduce risk of spread of invasive plants. | X |  | X | X |  |  |  | X | X |  |  |  | X
Use non-agricultural mulch materials for revegetation and sediment/erosion control. Non-agricultural products include wood straw or shred and wattles made from excelsior, wood or other non-agricultural materials. |  |  | X | X |  | X | X | X | X
Consultation with Denver Water Board shall occur for any project activities occurring within the FERC boundary for the Gross Reservoir Hydroelectric Project. | X | X | [14 empty] | X
There are several utility (electric, natural gas and communication) lines within the project area. Care shall be taken when working around these lines to avoid damage to them or their infrastructure. | X | X |  | X |  |  |  |  | X | [7 empty] | X
All recreation facilities (NFS roads, NFS trails, recreation sites) and infrastructure (such as gates, fences, sign kiosks, picnic tables) shall be protected from damage from all treatment activities. Any damaged facilities or infrastructure shall be repaired, replaced, or reconditioned to the level of the existing condition, or greater, to provide safe public access, as needed. Consult with Recreation Staff and/or Specialist as needed. |  |  | X | X |  |  |  |  | X | [5 empty] | X |  |  | X
High use public access portals (such as trailheads and highly traveled trail corridors) will not be used for fuels treatment project work or long term operations unless no other alternative exists. If used, safe public access on weekends will be provided. Fuels treatment work sites will be designed in a manner to allow safe public access even when occupied. Where this is not feasible, short-term forest orders closing fuels treatment areas to public access will be implemented, as needed, to ensure public safety, protect natural resources and improve effectiveness of project area objectives. Involve the Recreation Staff and/or Specialist through planning, implementation, and monitoring as needed. | X |  | X | X | X |  |  |  | X |  |  |  |  | X | X
Public notification shall occur prior to major project activities to raise public awareness. Local agency cooperators will be notified about the duration, intensity, and potential issues for the project work. |  | X |  | X | X | [8 empty] | X
Knolls (small rounded hilltops) and geologic features (rock outcrops) will be excluded from treatment to maintain aesthetic values. These features are identified as the highest point in the local vicinity that have a few trees exhibiting characteristics such as stunted growth, irregular crown shapes, and mature bark attributes. Treatment exclusions will extend down from the peak of the feature to the area where mechanical equipment can operate, approximately 40%, or the point where the vegetation transitions into a meadow dominated by grass and forbs. | X | [7 empty] | X | X |  |  |  |  | X
Manual Treatment Areas
Tree cutting of conifers can occur to the edge of the stream bank for perennial, intermittent and ephemeral streams. No woody riparian vegetation (e.g. willows, alders, river birch, etc.) shall be cut. Trees shall be directionally felled away from stream channels where practicable. | X |  | X | X |  |  | X |  | X | X
Retain all existing down woody material 5” DBH or greater within and up to 100 feet of riparian areas. This applies to portions of Units 40 and 74 where they overlap Preble’s meadow jumping mouse habitat. |  |  | X | X | X |  |  |  | X | X |  |  | X
Lopped and scattered slash shall be removed from the stream channel of perennial, intermittent and ephemeral streams. |  |  | X | X |  |  | X |  | X
No tree cutting shall occur within wetlands, fens, or wet meadows. These features may not be mapped, and may only be discovered during unit layout. | X |  | X | X |  |  | X |  | X | X
Mixed Conifer Areas
Trees shall be marked as either leave trees or cut trees, whichever is most efficient, prior to any cutting. | X | [7 empty] | X | X
Recognizing that not all units may have trees greater than 14 inches DBH, and to acknowledge the value of larger trees to the public, the diameter cut limit will be adjusted based on the existing condition while retaining 10% of the existing basal area in the largest diameter trees in each unit. The maximum diameter cut limit is 14 inches DBH. | X |  | X | X |  |  |  |  | X | X
Patchcut/Clearcut Areas
Retain coarse and fine woody debris (CWD and FWD) throughout clearcut/patchcut units to maintain long term soil productivity. a. At least 8 tons/acre of CWD , with preference for large diameter material (boles) b. At least 4 tons/acre of FWD |  |  | X | X |  |  | X |  | X | X | X
Involve a USFS Wildlife Biologist during layout of patchcuts/clearcuts to determine needs for narrow areas and/or island exclusions for wildlife crossing and cover. | X | [7 empty] | X | X |  |  | X
In general, locate openings away from system trails, or social trails that will be changed to system trails, once a Decision is made on the Magnolia Trails Project. A wildlife biologist shall approve locations of patchcuts and clearcuts in the vicinity of such trails. | X | [7 empty] | X | X |  |  | X |  | X
In order to meet scenery standards within the proposed patchcut/clearcut lodgepole pine dominated units, three to five uncut islands of trees must be retained within patchcut/clearcuts greater or equal to 5 acres in size. These islands shall be at least ½ acre in size and total 25% of the appropriate patchcut/clearcut area within each unit. The acreage within the islands will not decrease the number of overall acres to be cut within a designated patch/clearcut unit. For example in unit 11 (20 acres), 30% or 6 acres of the unit could be cut utilizing a combination of patchcut/clearcuts. To equate to a one 6-acre clearcut that is treated, the boundary of the clearcut will encompass 7.5 acres to account for the 25% acre retention to be included without changing the intent of reducing the overall acreage by 30%. | X |  | X | X |  |  |  |  | X | X | [8 empty] | X
Retain all areas of mixed conifer inclusions ½ acre or less in lodgepole pine stands. If the inclusion is larger, thinning as prescribed could be implemented. An exception is cutting trees for skid trails and landings. | X | [7 empty] | X | X |  |  | X
Old Growth/Effective Habitat/Interior Forest Areas
In Management Area 3.5, exclude vegetation treatment from inventoried or discovered lodgepole pine old growth per Forest Plan standard. Exceptions may be made if the lodgepole old growth is considered non-functional at time of implementation. This determination of functionality is to be made for the stand as a whole within the treatment unit. | X |  |  | X |  |  |  |  | X | X |  |  | X
Where effective habitat occurs in treatment units, unit boundaries and/or canopy cover reduction may be modified as determined by a wildlife biologist, if needed to maintain these habitats. | X |  |  | X |  |  |  |  | X | X |  |  | X
Within mapped interior forest and within a 328 foot buffer around mapped interior forest, retain at least 40% canopy cover. Exceptions may occur based on involvement of wildlife biologist and silviculturist and use of updated USFS data. | X |  |  | X |  |  |  |  | X | X |  |  | X
Retain a minimum of 5 of the largest available dead trees, minimum 8” DBH for lodgepole and 10” for ponderosa pine and Douglas-fir, per acre, as an average across old growth retention and inventoried stands within a treatment unit. Give preference to retaining ponderosa pine snags where available. Criteria for snag selection will be specified in the silviculture prescription with emphasis on retaining the largest diameter snags present. If the minimum number of snags is not available, then the largest available live, green replacement trees will be retained for future snags. |  |  | X | X |  |  |  |  | X | X |  |  | X
Slash Piles
Hand constructed burn piles shall be located at least 50 feet from perennial streams, wetlands, fens, wet meadows, and aspen stands. For intermittent and ephemeral streams, burn piles shall be located 50 feet from the stream or outside the inner gorge, whichever is less. For Preble’s meadow jumping mouse, piles shall be located at least 100 feet from the edge of the water around Winiger Gulch and the unnamed southern tributary to Winiger Gulch. If it not practicable to locate piles sufficiently away from streams, or if doing so will violate other requirements (e.g. minimum spacing between piles, minimum distance from residual trees), do not cut the water adjacent trees, unless approved by a USFS Soil Scientist, Hydrologist, or Fish Biologist. | X |  | X | X |  |  | X |  | X | X |  |  | X
To minimize long term effects of pile burning, watershed, botany and/or implementation personnel will conduct surveys to identify if and where burn pile restoration actions are needed following pile burning activities. Any combination of the following restoration actions will be recommended if/where needed: a. Tilling/scarifying after burning to promote recovery by breaking up water repellent layers, increasing water infiltration, and mixing in organic material from areas adjacent to the pile. b. Weed treatments c. Seeding d. Covering with litter, duff and/or slash |  |  |  |  | X | X | X | X
Burn piles should be located out of sight of major viewpoints as designated by a USFS Landscape Architect whenever possible within the constraints of the contract. |  | X | X | X |  |  |  |  | X | [9 empty] | X
In treatment units where slash is piled by hand, leave an average of 2 piles per acre for wildlife habitat, including any piles remaining from previous vegetation treatment, distributed randomly throughout the unit. |  |  |  |  | X |  |  |  | X |  |  | X | X
Minimum pile size, hand or machine created, shall be no less than 6 feet high by 6 feet wide. |  |  | X | X |  |  |  |  | X |  | X
Consult USFS Fuels Specialist during contract preparation for current maximum pile size and pile separation requirements as regulated by the Colorado Air Pollution Control Division. |  | X | [6 empty] | X |  | X | X
Piles shall be constructed in a manner to minimize large air spaces and dirt within the piles. Piles shall not have material extending more than 4 feet in any direction beyond the pile perimeter and a minimum of 4 feet of separation from pile perimeter to surrounding down woody material to reduce unwanted fire spread. |  |  | X | X |  |  |  |  | X |  | X | X
Construct a minimum of a 6 foot wide control line, down to bare mineral soil, around each machine pile to create separation between piled material and surrounding slash mat. If piles are grouped, a single control line may be placed around the entire group rather than around individual piles. The scraped material must be moved outward to avoid a berm adjacent to the piles’ edge. |  |  | X | X |  |  |  |  | X |  | X | X
In manual units, pile sound, existing and/or created slash material, 1” to 6” diameter and 2 feet or longer. Alternatively, any slash that must be moved more than 50 feet to meet minimum required pile size may be lopped and scattered to a maximum depth of 18”. Lopped and scattered material is expected to be a rare occurrence and most likely occur in very open grown areas where a few trees are required to be cut to meet spacing specifications, but not enough trees are cut to produce enough slash to create a minimum sized pile. |  |  | X | X |  |  |  |  | X |  | X
Timing Restrictions
Avoid treatment operations from May 1 through August 10 in flammulated owl territories. Avoidance areas will be determined by a USFS Wildlife Biologist based on survey results, flammulated owl territory size, topography, and vegetation. Prescribed burning operations may be conducted if determined to be appropriate by a USFS Wildlife Biologist. This applies to most units in the Winiger Ridge and South Winiger areas, and may apply to other areas if appropriate based on survey results. |  |  | X | X | X |  |  |  | X |  |  |  | X
Raptor nest areas, including species-specific buffers, will generally have no treatment activity from March 1 through September 15, depending on species, or until determined unoccupied by the wildlife biologist. Access through buffers during this period will be assessed by a USFS Wildlife Biologist. a. If known nests become unoccupied, additional surveys will be conducted during the breeding season prior to any project activity. The extent and timing of surveys will be determined by a USFS Wildlife Biologist. b. Units with suitable nest habitat will also be resurveyed for new nest locations prior to implementation. If a new active nest is detected during surveys or becomes known by other means, appropriate mitigations will be implemented. c. For northern goshawk nests including alternate nest sites, exclude treatment in up to a 30-acre area containing the nest tree. Site-specific exclusion areas will be determined by a USFS Wildlife Biologist based on topography, vegetation and other factors. Outside of the breeding season, generally from September 16 through February 28, limited thinning may be allowed within this area if determined necessary to help reduce the risk of losing the nest site to wildfire. A USFS Wildlife Biologist will help design and approve treatment. | X | X | X | X | X |  |  |  | X |  |  |  | X
Unless a site-specific exception is determined to be appropriate by a USFS Wildlife Biologist, avoid treatment from December 1 through March 30 in elk severe winter range and winter concentration areas. These areas are based on the most current available mapping data from Colorado Parks and Wildlife. |  |  | X | X | X |  |  |  | X |  |  |  | X
Project operations will not be conducted on Memorial Day, 4th of July and Labor Day holiday weekends and on Sundays. Operating times for heavy equipment and chainsaws shall be limited to the hours of 7 a.m. to 7 p.m. |  |  | X | X |  |  |  |  | X | [5 empty] | X
Piles outside the 100 foot riparian buffer but within 328 feet of the stream channel may only be burned from November 1 through April 30 during Preble’s meadow jumping mouse hibernation. This applies to Units 40 and 74. |  |  |  |  | X | [6 empty] | X | X

## Phase 2 Design Criteria
Forsythe II Crosswalk
Phase 2 Design Criteria
Design Criteria | Where Addressed | [5 empty] | Verified By | [12 empty] | Initials/Date | Comments
| Layout | Prior to Implementation | Statement of Work in Contract | Implementation | Burn Plan | Post Treatment | Soils / Hydrologist / Fisheries | Botanist / Noxious Weeds | Pre-Sale Forester / Contract Administrator | Silviculturist | Fuels Specialist | Burn Boss | Wildlife | PAO | Recreation | Archeologist | Lands | Engineering | Landscape Arch
All Treatment Areas
Following project implementation, at least 70% effective ground cover should be maintained within mechanical and manual treatment units to lower the risk of soil erosion. Effective ground cover includes surface rock cover, pine needle cover, and cover provided by low lying vegetation and mulch. |  |  | X | X |  | X | X | X | X
In chipped areas, chip depth shall average less than 3”. Chip depth of up to 5” may occur over small areas (not to exceed 5% of the treatment unit). Chips shall be distributed in a mosaic pattern over no more than 30% of the activity area. |  |  | X | X |  |  | X | X | X
In masticated areas, chunks shall be distributed to avoid dense accumulations that could potentially impede growth of native grasses, forbs or seedlings. |  |  | X | X |  |  | X | X | X
All treatment areas will be reviewed by a USFS Landscape Architect prior to final unit layout. Unit boundaries shall be natural edges whenever possible and prevent the appearance of uniform tree spacing and straight line unit boundaries. Straight line boundaries shall be treated by ‘feathering’ and ‘scalloping’. | X |  |  | X |  |  |  |  | X | [9 empty] | X
Minimize damage to aspen 8” DBH and larger. |  |  | X | X |  |  |  |  | X |  |  |  | X
Leave live and dead wildlife trees as individually designated by a USFS Wildlife Biologist and/or according to marking guidelines agreed to in coordination with a USFS Wildlife Biologist, Silviculturist, Fuels Planner, and prep crews. Leave trees may include trees with cavities, trees with large squirrel middens, and/or Abert’s squirrel nest trees. | X | X | X | X |  |  |  |  | X | X |  |  | X
Within treatment units where Rocky Mountain juniper occurs, leave an average of one large individual, or clump of three or more if available, Rocky Mountain Juniper per acre. | X |  | X | X |  |  |  |  | X | X |  |  | X
If a federally listed or USFS sensitive wildlife species is identified within treatment units or areas potentially impacted by proposed project activities prior to or during implementation, a USFS Wildlife Biologist will be contacted as soon as possible to ensure Forest Plan direction and Endangered Species Act requirements are met. | X | X | X | X |  |  |  |  | X |  |  |  | X
If raptor nesting activity (e.g. nesting behavior, nest sites, or fledglings) is detected within treatment units or areas potentially impacted by proposed project activities prior to or during implementation, a USFS Wildlife Biologist will be contacted as soon as possible to ensure Forest Plan direction for nesting raptor protection are met. | X | X | X | X |  |  |  |  | X |  |  |  | X
Retain a minimum of 5 of the largest available dead trees, in clumps where available, minimum 8” DBH for lodgepole and 10” for ponderosa pine and Douglas-fir, per acre, as an average across each treatment unit. Give preference to retaining ponderosa pine snags where available. Criteria for snag selection will be specified in the silviculture prescription with emphasis on retaining the largest diameter snags present. If the minimum number of snags is not available, then the largest available live, green replacement trees will be retained for future snags. | X | X | X | X |  |  |  |  | X | X |  |  | X
Retain a minimum of 5 logs and 100 linear feet per acre of existing down logs distributed randomly across each unit, with a minimum diameter of 8” for lodgepole pine and 10” for other conifer species. Do not cut live trees to meet this criterion, except where live trees will be cut according to the prescription in lodgepole pine patchcuts and clearcuts. Jackstrawed bole wood, created by treatment, 6” in diameter or greater and left in the unit must be scattered and be in contact with the ground. Individual boles of 6” or greater can be left unbucked. |  |  | X | X |  |  |  |  | X | X |  |  | X
Within flammulated owl territories: a. Thin small and medium sized trees to maintain large-open grown canopies. b. Retain live trees, 12” DBH and greater, including on ridgelines. c. In riparian areas, leave all trees with existing cavities and remove conifers less than 8” DBH except those with cavities. | X |  | X | X |  |  |  |  | X |  |  |  | X
All treatment units adjacent to existing raptor nests will be resurveyed the nesting season prior to implementation. This is to ensure that the birds have not moved their nests into an active unit. |  | X | [6 empty] | X |  |  |  | X
Buffer known roost locations for Fringed myotis bat and Townsend’s big-eared bat from treatment activities during key activity times. Prescribed burning should avoid smoke saturation of roost sites during key activity times. |  | X | X | X | X |  |  |  | X |  |  | X | X
Sensitive plant species and species of local concern locations will be determined by a USFS Botanist and designated buffers will be applied. | X |  | X | X |  |  |  | X | X
All areas potentially impacted by proposed project activities that have not been surveyed for rare plants and that contain high-quality suitable habitat for sensitive and local concern plant species will be surveyed in such habitat prior to disturbance activities. | X | [6 empty] | X | X
To minimize risk of noxious weed introduction and spread, require all equipment to be used for ground-disturbing activities for this project (not including service trucks or other vehicles that remain on roadways) to be cleaned, i.e., free of mud, dirt, plant parts, and seeds, or other debris that could contain or hold seeds, prior to entering the project area. All wheeled or tracked vehicles, including trailers, or other equipment entering constructed temporary roads shall be cleaned prior to entry to the project area. Equipment will be considered free of soil and other debris when a visual inspection does not disclose such material. Equipment shall be re-cleaned prior to transfer from a unit where noxious weeds are known to be present into a unit where noxious weeds are not known present. |  |  | X | X |  |  |  | X | X
For known weed occurrences and for any new noxious weed infestations found in or near units prior to or during implementation of vegetation treatment, implementation personnel will coordinate with USFS District Invasive Plants Coordinator to implement appropriate prevention measures, such as avoidance, treatment of weeds prior to fuels implementation, and/or additional equipment cleaning requirements, such as between infested and uninfested units. | X | X | X | X |  | X |  |  | X
Coordinate with USFS District Invasive Plants Coordinator to locate landings, staging areas, skid trails, burn piles, and other areas of severe soil disturbance to best reduce risk of spread of invasive plants. | X |  | X | X |  |  |  | X | X |  |  |  | X
Use non-agricultural mulch materials for revegetation and sediment/erosion control. Non-agricultural products include wood straw or shred and wattles made from excelsior, wood or other non-agricultural materials. |  |  | X | X |  | X |  | X | X
To avoid damage to the Boulder Gravity Line, driving across the line shall be avoided. | X |  |  | X |  |  |  |  | X | [7 empty] | X
Consultation with Denver Water Board shall occur for any project activities occurring within the FERC boundary for the Gross Reservoir Hydroelectric Project. | X | X | [14 empty] | X
There are several utility (electric, natural gas and communication) lines within the project area. Care shall be taken when working around these lines to avoid damage to them or their infrastructure. | X | X |  | X |  |  |  |  | X | [7 empty] | X
All recreation facilities (NFS roads, NFS trails, recreation sites) and infrastructure (such as gates, fences, sign kiosks, picnic tables) shall be protected from damage from all treatment activities. Any damaged facilities or infrastructure shall be repaired, replaced, or reconditioned to the level of the existing condition, or greater, to provide safe public access, as needed. Consult with Recreation Staff and/or Specialist as needed. |  |  | X | X |  |  |  |  | X | [5 empty] | X |  |  | X
High use public access portals (such as trailheads and highly traveled trail corridors) will not be used for fuels treatment project work or long term operations unless no other alternative exists. If used, safe public access on weekends will be provided. Fuels treatment work sites will be designed in a manner to allow safe public access even when occupied. Where this is not feasible, short-term forest orders closing fuels treatment areas to public access will be implemented, as needed, to ensure public safety, protect natural resources and improve effectiveness of project area objectives. Involve the Recreation Staff and/or Specialist through planning, implementation, and monitoring as needed. | X |  | X | X | X |  |  |  | X |  |  |  |  | X | X
Public notification shall occur prior to major project activities to raise public awareness. Local agency cooperators will be notified about the duration, intensity, and potential issues for the project work. |  | X |  | X | X | [8 empty] | X
Knolls (small rounded hilltops) and geologic features (rock outcrops) will be excluded from treatment to maintain aesthetic values. These features are identified as the highest point in the local vicinity that have a few trees exhibiting characteristics such as stunted growth, irregular crown shapes, and mature bark attributes. Treatment exclusions will extend down from the peak of the feature to the area where mechanical equipment can operate, approximately 40%, or the point where the vegetation transitions into a meadow dominated by grass and forbs. | X | [7 empty] | X | X |  |  |  |  | X
Mechanical Treatment Areas
No mechanical logging equipment (e.g. feller-bunchers, skidders, etc.) shall be permitted to operate within a 100 foot buffer from the edge of the water around perennial streams, intermittent streams, lakes, ponds, wetlands, fens, or wet meadows. A no mechanical treatment buffer of 328 feet (100 meters) from the edge of the water shall be established around Winiger Gulch and the unnamed southern tributary to Winiger Gulch as shown in the attached map. Activities that shall be excluded from the buffer include: • Mechanical fuels treatment operations using heavy equipment • Machine piles • Vehicle service and fueling areas • Driving tracked or wheeled machinery except along existing roads, in the southwest corner of Unit 40 and the northeast corner of Unit 74 where they overlap mapped Preble’s meadow jumping mouse habitat. | X |  | X | X |  |  | X | X | X |  |  |  | X
For ephemeral streams, equipment shall be excluded from the stream channel, except to cross at points designated by a USFS Contract or Sale Administrator(s). | X |  | X | X |  |  | X |  | X
Limit operation of heavy equipment to slopes of less than 30%. Slopes up to 40% may be considered on a site specific basis and will require evaluation by a Soils Scientist. | X |  | X | X |  |  | X |  | X | X
Slash take back will only be allowed on skid trails, in patchcut/clearcut units where it is needed to meet the coarse and fine woody debris retention criteria (see Patchcut/Clearcut Areas, 1a and 1b, in this document), or other areas designated as adversely impacted by a USFS Soil Scientist/Hydrologist/COR/Sale Administrator, for soil stabilization, and to a maximum depth of 18 inches. |  |  | X | X |  |  | X |  | X | X | X
A cultural resource inventory will be completed on all units that have been identified by a USFS Archaeologist in consultation with the SHPO. The survey and reports will be completed and sent to the SHPO prior to project implementation. Implementation will not begin until the SHPO has concurred with a determination of no historic properties affected or no historic properties adversely affected. | X | X |  |  | X |  |  |  | X | X | [5 empty] | X
Sites located during the field inventory that are evaluated as eligible for the NRHP, will have a 50 foot buffer placed around the exterior site boundary. No mechanical treatment will occur within the site boundary and the 50 foot buffer. When treatment is necessary, eligible sites and the 50 foot buffer will be hand treated for hazard trees and accumulated fuel build up by hand felling trees. Slash will either be hand piled for chipping and/or bucked up by hand, and loaded onto rubber tired vehicles to be hauled to designated burn piles for burning. No thinning, pile burning, or other slash treatments will occur within these buffers unless determined to be appropriate by a USFS Archaeologist. | X | X |  | X |  |  |  |  | X | X | [5 empty] | X
All NRHP eligible or unevaluated sites within the units proposed for mechanical treatments will be flagged on the ground for avoidance during implementation. | X | X | X | X |  |  |  |  | X | X | [5 empty] | X
Previously undiscovered sites encountered during the course of project activities will be avoided until they can be evaluated by a USFS Archaeologist. If affected properties are discovered after project activities are completed, the USFS will document any damage and consult with SHPO and Council pursuant to the procedures in 36CFR Part 800.13(b). |  |  |  | X |  |  |  |  | X | [6 empty] | X
Mixed Conifer Areas
Trees shall be marked as either leave trees or cut trees, whichever is most efficient, prior to any cutting. | X | [7 empty] | X | X
Recognizing that not all units may have trees greater than 14 inches DBH, and to acknowledge the value of larger trees to the public, the diameter cut limit will be adjusted based on the existing condition while retaining 10% of the existing basal area in the largest diameter trees in each unit. The maximum diameter cut limit is 14 inches DBH. | X |  | X | X |  |  |  |  | X | X
Patchcut/Clearcut Areas
Retain coarse and fine woody debris (CWD and FWD) throughout clearcut/patchcut units to maintain long term soil productivity. a. At least 8 tons/acre of CWD , with preference for large diameter material (boles) b. At least 4 tons/acre of FWD |  |  | X | X |  |  | X |  | X | X | X
Involve a USFS Wildlife Biologist during layout of patchcuts/clearcuts to determine needs for narrow areas and/or island exclusions for wildlife crossing and cover. | X | [7 empty] | X | X |  |  | X
In general, locate openings away from system trails, or social trails that will be changed to system trails, once a Decision is made on the Magnolia Trails Project. A wildlife biologist shall approve locations of patchcuts and clearcuts in the vicinity of such trails. | X | [7 empty] | X | X |  |  | X
In order to meet scenery standards within the proposed patchcut/clearcut lodgepole pine dominated units, three to five uncut islands of trees must be retained within patchcut/clearcuts greater or equal to 5 acres in size. These islands shall be at least ½ acre in size and total 25% of the appropriate patchcut/clearcut area within each unit. The acreage within the islands will not decrease the number of overall acres to be cut within a designated patch/clearcut unit. For example in unit 11 (20 acres), 30% or 6 acres of the unit could be cut utilizing a combination of patchcut/clearcuts. To equate to a one 6-acre clearcut that is treated, the boundary of the clearcut will encompass 7.5 acres to account for the 25% acre retention to be included without changing the intent of reducing the overall acreage by 30%. | X |  | X | X |  |  |  |  | X | X | [8 empty] | X
Retain all areas of mixed conifer inclusions ½ acre or less in lodgepole pine stands. If the inclusion is larger, thinning as prescribed could be implemented. An exception is cutting trees for skid trails and landings. | X | [7 empty] | X | X |  |  | X
Old Growth/Effective Habitat/Interior Forest Areas
In Management Area 3.5, exclude vegetation treatment from inventoried or discovered lodgepole pine old growth per Forest Plan standard. Exceptions may be made if the lodgepole old growth is considered non-functional at time of implementation. This determination of functionality is to be made for the stand as a whole within the treatment unit. | X |  |  | X |  |  |  |  | X | X |  |  | X
Where effective habitat occurs in treatment units, unit boundaries and/or canopy cover reduction may be modified as determined by a wildlife biologist, if needed to maintain these habitats. | X |  |  | X |  |  |  |  | X | X |  |  | X
Within mapped interior forest and within a 328 foot buffer around mapped interior forest, retain at least 40% canopy cover. Exceptions may occur based on involvement of wildlife biologist and silviculturist and use of updated USFS data. | X |  |  | X |  |  |  |  | X | X |  |  | X
Retain a minimum of 5 of the largest available dead trees, minimum 8” DBH for lodgepole and 10” for ponderosa pine and Douglas-fir, per acre, as an average across old growth retention and inventoried stands within a treatment unit. Give preference to retaining ponderosa pine snags where available. Criteria for snag selection will be specified in the silviculture prescription with emphasis on retaining the largest diameter snags present. If the minimum number of snags is not available, then the largest available live, green replacement trees will be retained for future snags. |  |  | X | X |  |  |  |  | X | X |  |  | X
Slash Piles
To the extent practicable, construct machine slash piles on landings. If machine piling is done off landings, conduct piling to leave topsoil in place and to avoid displacement of topsoil. Machinery that lifts and places material into burn piles is recommended over machinery that pushes or drags material into burn piles. |  |  | X | X |  |  | X |  | X | X | X
Hand constructed burn piles shall be located at least 50 feet from perennial streams, wetlands, fens, wet meadows, and aspen stands. For intermittent and ephemeral streams, burn piles shall be located 50 feet from the stream or outside the inner gorge, whichever is less. For Preble’s meadow jumping mouse, piles shall be located at least 100 feet from the edge of the water around Winiger Gulch and the unnamed southern tributary to Winiger Gulch. If it not practicable to locate piles sufficiently away from streams, or if doing so will violate other requirements (e.g. minimum spacing between piles, minimum distance from residual trees), do not cut the water adjacent trees, unless approved by a USFS Soil Scientist, Hydrologist, or Fish Biologist. | X |  | X | X |  |  | X | X | X | X |  |  | X
To minimize long term effects of pile burning, watershed, botany and/or implementation personnel will conduct surveys to identify if and where burn pile restoration actions are needed following pile burning activities. Any combination of the following restoration actions will be recommended if/where needed: a. Tilling/scarifying after burning to promote recovery by breaking up water repellent layers, increasing water infiltration, and mixing in organic material from areas adjacent to the pile. b. Weed treatments c. Seeding d. Covering with litter, duff and/or slash |  |  |  |  | X | X | X | X
Burn piles should be located out of sight of major viewpoints as designated by a USFS Landscape Architect whenever possible within the constraints of the contract. |  | X | X | X |  |  |  |  | X | [9 empty] | X
In treatment units where slash is piled by hand, leave an average of 2 piles per acre for wildlife habitat, including any piles remaining from previous vegetation treatment, distributed randomly throughout the unit. |  |  |  |  | X |  |  |  | X |  |  | X | X
Minimum pile size, hand or machine created, shall be no less than 6 feet high by 6 feet wide. |  |  | X | X |  |  |  |  | X |  | X
Consult USFS Fuels Specialist during contract preparation for current maximum pile size and pile separation requirements as regulated by the Colorado Air Pollution Control Division. |  | X | [6 empty] | X |  | X | X
Piles shall be constructed in a manner to minimize large air spaces and dirt within the piles. Piles shall not have material extending more than 4 feet in any direction beyond the pile perimeter and a minimum of 4 feet of separation from pile perimeter to surrounding down woody material to reduce unwanted fire spread. |  |  | X | X |  |  |  |  | X |  | X | X
Construct a minimum of a 6 foot wide control line, down to bare mineral soil, around each machine pile to create separation between piled material and surrounding slash mat. If piles are grouped, a single control line may be placed around the entire group rather than around individual piles. The scraped material must be moved outward to avoid a berm adjacent to the piles’ edge. |  |  | X | X |  |  |  |  | X |  | X | X
In machine units, reasonably gather and place activity slash material, 1” to 6” diameter, into piles. If more than 50% of a treatment unit has continuous slash depth greater than 6” after initial treatment, additional piling will be required. |  |  | X | X |  |  |  |  | X |  | X
In manual units, pile sound, existing and/or created slash material, 1” to 6” diameter and 2 feet or longer. Alternatively, any slash that must be moved more than 50 feet to meet minimum required pile size may be lopped and scattered to a maximum depth of 18”. Lopped and scattered material is expected to be a rare occurrence and most likely occur in very open grown areas where a few trees are required to be cut to meet spacing specifications, but not enough trees are cut to produce enough slash to create a minimum sized pile. |  |  | X | X |  |  |  |  | X |  | X
Locate machine piles a minimum of 150 feet and hand piles a minimum of 50 feet from any infrastructure or private property boundary. |  |  | X | X |  |  |  |  | X |  | X | X
Timing Restrictions
Avoid treatment operations from May 1 through August 10 in flammulated owl territories. Avoidance areas will be determined by a USFS Wildlife Biologist based on survey results, flammulated owl territory size, topography, and vegetation. Prescribed burning operations may be conducted if determined to be appropriate by a USFS Wildlife Biologist. This applies to most units in the Winiger Ridge and South Winiger areas, and may apply to other areas if appropriate based on survey results. |  |  | X | X | X |  |  |  | X |  |  |  | X
Raptor nest areas, including species-specific buffers, will generally have no treatment activity from March 1 through September 15, depending on species, or until determined unoccupied by the wildlife biologist. Access through buffers during this period will be assessed by a USFS Wildlife Biologist. a. If known nests become unoccupied, additional surveys will be conducted during the breeding season prior to any project activity. The extent and timing of surveys will be determined by a USFS Wildlife Biologist. b. Units with suitable nest habitat will also be resurveyed for new nest locations prior to implementation. If a new active nest is detected during surveys or becomes known by other means, appropriate mitigations will be implemented. c. For northern goshawk nests including alternate nest sites, exclude treatment in up to a 30-acre area containing the nest tree. Site-specific exclusion areas will be determined by a USFS Wildlife Biologist based on topography, vegetation and other factors. Outside of the breeding season, generally from September 16 through February 28, limited thinning may be allowed within this area if determined necessary to help reduce the risk of losing the nest site to wildfire. A USFS Wildlife Biologist will help design and approve treatment. | X | X | X | X | X |  |  |  | X |  |  |  | X
Unless a site-specific exception is determined to be appropriate by a USFS Wildlife Biologist, avoid treatment from December 1 through March 30 in elk severe winter range and winter concentration areas. These areas are based on the most current available mapping data from Colorado Parks and Wildlife. |  |  | X | X | X |  |  |  | X |  |  |  | X
Project operations will not be conducted on Memorial Day, 4th of July and Labor Day holiday weekends and on Sundays. Operating times for heavy equipment and chainsaws shall be limited to the hours of 7 a.m. to 7 p.m. |  |  | X | X |  |  |  |  | X | [5 empty] | X
Piles outside the 100 foot riparian buffer but within 328 feet of the stream channel may only be burned from November 1 through April 30 during Preble’s meadow jumping mouse hibernation. This applies to Units 40 and 74. |  |  |  |  | X | [6 empty] | X | X
Roads/Skid Trails/Temp Roads/Landings/Equipment Use
Temporary roads, skid trails, landing areas, and equipment use in mechanical treatment units shall be subject to operating equipment restrictions to protect soil and water. Operate heavy equipment only when soil moisture in the upper 6 inches is below the plastic limit (a ball can be formed in the fist that holds together on gentle tossing or shaking) OR protected by at least one foot of packed snow or 2 inches of frozen soil. This may mean temporary restriction on equipment operation and travel within the treatment area in periods of heavy rains and snow or when soils are wet. |  |  |  | X |  |  | X |  | X | [8 empty] | X
The USFS shall approve locations of skid trails and landings prior to treatment. Re-use existing skid trails as much as practicable to minimize new disturbance. Within mapped effective habitat, a USFS Wildlife Biologist will approve locations of skid trails and landings. |  |  | X | X |  |  |  |  | X |  |  |  | X |  | X
All temporary road construction, including skid trails, shall be obliterated within one year of completion of use, including pile burning. Project implementation, watershed, soil, and engineering personnel shall cooperate to determine appropriate obliteration methods. a. Temporary road surfaces, including skid trails and landings, shall be decompacted along the entire road/skid trail length or landing area unless waived by Soil Scientist. Roads that were constructed with cut and fill shall be partially or fully recontoured or pitted. Roads that were constructed on the natural ground contour shall be pitted, subsoiled, or ripped. • Partial recontouring of the road prisms shall be utilized in areas where it is not feasible or beneficial to disturb soils previously unaffected by construction operations to stabilize a decommissioned temporary road. Factors such as steep slopes, large amounts of rock, or vegetation may impact a decision to utilize partial recontouring. Partial recontouring shall use available fill material from original construction. Fills shall be returned to, and compacted into, the cut removal area. No further ground disturbance involving cutting material shall occur. Handle soil to ensure that minimal segregation of materials occurs. Compaction may be by machine track or bucket. The recontoured surface shall be outsloped a minimum of 5% for the entire road prism width and no berms shall remain. Finished grades shall minimize drainage following the contour of the road, where necessary grade dips shall be installed along the grade to direct drainage off the disturbed area. Where high cut slopes are present, continue pulling up fill material and backfilling cut removal areas until no cut slope remains greater than 1:1 H:V in slope and two feet in height. • Full recontouring of the road prisms shall be utilized in decommissioning temporary road segments where it is both feasible and advantageous to disturb soil previously unaffected by construction operations to completely recontour the road. Full recontouring shall include pull up of all fill material and place/compact into the cut removal area. Very little disturbance of the natural ground under the fill shall occur. The final slope area, over the entire width of the road prism, shall reproduce the pre-road natural slope. It shall blend in with the surrounding slope and no berms or windrows of any material shall remain. | [5 empty] | X | X | X | X | [5 empty] | X |  |  | X | X
b. Where applicable, remove all temporary stream crossings and restore stream bed and banks. c. Restore natural drainage patterns across the road template. d. Provide effective closure at junctions with open roads and NFS trails to prevent unauthorized use. Effective closure techniques may include recontouring or pitting for site distance, fencing, gates, berms, barrier rocks of various sizes (median size of 2.5 ft. x 2.5 ft. x 2.5 ft. [1 ton], grouped in natural arrangements and 1/3-1/2 buried), plantings, and/or felled trees. e. Scatter slash on restored disturbance. f. Restore ground cover using native seed or plants, methods and timing, and soil amendments as practicable to meet revegetation objectives and in consultation with a USFS Botany Representative. Use government furnished seed when available.
Vegetation treatment implementation and related contracting will incorporate use of existing and/or previously used areas as much as possible for fuels treatment operations, in order to reduce the amount of new disturbance which usually leads to new “social” routes being created. Any non-system roads which are used for access to fuels treatment units shall be considered to be temporary roads and shall be obliterated following the design criteria for temporary roads. | X |  |  | X |  | X |  |  | X | [5 empty] | X
Where topsoil depth exceeds 2”, topsoil shall be salvaged and stockpiled from all areas to be disturbed by construction of temporary roads and road improvements and shall be incorporated into the reclamation. |  |  | X | X |  | X | X |  | X
Temporary road construction shall be kept to the minimum construction possible to accommodate intended use and shall meet the following guideline. a. Roads shall not follow fall line of the land but shall traverse contours to minimize slopes. Generally, slopes of 10 percent or less shall be maintained, however reaches of 200 feet or less may be up to 14 percent in slope. b. Road alignment shall be selected to minimize cuts and fills to 2-foot maximum. c. Road widths shall be the minimum required for the equipment and shall not exceed 15 feet. d. Roads shall be outsloped where possible and rolling dips shall be constructed instead of ditches and culverts, wherever practicable, as necessary to control sediment and erosion. Drainage features shall not drain directly into streams. Best Management Practices shall be employed at the termination of drainage features to protect vegetation from sedimentation. |  |  | X | X |  |  |  |  | X | [8 empty] | X
Construction of temporary roads and road improvements shall to the extent possible minimize ground disturbance, avoid crossings of drainages, provide buffers to drainages and sensitive areas, avoid steep slopes, avoid wet areas and swale bottoms, avoid unstable slopes, and shall minimize erosion potential and sedimentation of water ways. |  |  | X | X |  |  | X |  | X | [8 empty] | X
If material will be imported for road base or other uses, developed borrow sources or pit-run material sources will be inspected for weeds, weed parts or weed seeds by either a Forest Service employee or other party approved by the Forest Service. Aggregate base or riprap sourced from commercial pits does not need to be inspected. |  |  | X | X |  |  |  | X | X
Planning, construction and maintenance of temporary roads shall include sediment and erosion controls as necessary to prevent resource damage. Such controls are to be maintained and supplemented as necessary through the life of the project. |  |  | X | X |  |  | X | X | X | [8 empty] | X
Prior to the construction on NFS land of any egress route from Big Springs subdivision, the Forest shall approve locations, plans, best management practices, storm water management plans, and any other plans necessary to protect NFS lands and resources. Resource protection measures shall be installed and maintained during construction and for a sufficient time after construction until the site has stabilized. | X | X |  | X |  |  | X |  | X | [7 empty] | X | X
System roads shall not be used during winter and wet periods when there is a reduction in the ability of the road or road structure to support traffic, provide drainage, or provide safe transportation. Examples of reduction in the support value or safety of the roadway include, but are not limited to, soil, mud, debris, or oversized rocks incorporated into the roadway that affect drainage, normal maintenance activities, or the strength of the surface structure; intermixing of slash or subgrade soil with aggregate base; severe alteration of drainage that leads to surface aggregate loss, changes in character of ditches or drainage structures, or concentration of water that harms streams or water sources; accelerated breakdown of asphalt surfaces. If removal of snow from system roads for winter operations is allowed, provide adequate maintenance to maintain the road surface structure, drainage of the roadway, and safe passage for vehicles. Snow storage areas shall be approved by the USFS. Avoid riparian areas, wetlands or streams for snow storage to the extent possible. Space, construct, and maintain drainage holes in the dike of snow or berm caused by snow removal operations. Place drain holes to obtain surface drainage without discharging on erodible fills. Perform maintenance work in a manner to preserve and protect roads and appurtenances, and prevent erosion damage to streams and other Forest values. Any type of equipment to remove snow may be utilized provided: a. The equipment is of the size and type commonly used to remove snow and will not cause damage to the road surface or structure. b. The use of plows or dozers to remove snow requires written approval by the USFS. Equip plows or dozers with shoes or runners to keep the dozer blade a minimum of 2 inches above the road surface. |  |  | X | X |  |  | X |  | X | [8 empty] | X
Existing road conditions shall be assessed prior to implementation for all roads to be used for the project including County and private roads used to access National Forest lands. Roads shall be maintained in their existing condition through-out the project, if any widening or other improvements are required for the project these improvements shall be assessed at the completion of the project to determine if they are acceptable or need to be removed. |  | X | X | X |  | X |  |  | X | [8 empty] | X
When the work is complete the existing roads shall be inventoried to ensure drainage is operational and road surface is intact. | [5 empty] | X |  |  | X | [8 empty] | X
Unless the condition of an existing road is suitable for truck and trailer traffic, mechanized equipment shall be ‘walked’ (travel under its own power as opposed to transported on a trailer) into any units where mechanical treatments is planned. |  |  | X | X |  |  |  |  | X | [8 empty] | X
Coordinate all work and traffic that impacts County roads, including hauling, with the County ahead of the work commencing. Obtain County permits as necessary. |  | X |  | X |  |  |  |  | X |  |  |  |  | X |  |  |  | X
Coordinate with road users, who will be impacted by the work, obtain access as necessary and contact information for any temporary closures or other coordination. |  | X |  | X |  |  |  |  | X |  |  |  |  | X
All roads impacted by project activities shall have warning signs and traffic control as follows: a. In accordance with the “Manual of Uniform Traffic Control Devices.” b. Maintained for through traffic during felling, slash treatment, and/or removal operations. c. Left in an operational condition that will adequately accommodate traffic at the end of each work day. d. Have barricades erected and/or proper signs placed at any traffic hazards in or adjacent to the road at the end of each workday. e. All felled trees shall be decked or removed and slash piled or removed from the bladed, mowed, or brushed road corridor each day. |  |  | X | X |  |  |  |  | X | [8 empty] | X
Linear woody material designated to remain from roadway clearing activities shall be placed outside the clearing limits in close contact with, and perpendicular to, the slope. All other available organic and inorganic debris shall be scattered evenly outside of the clearing limits. |  |  | X | X |  | X |  |  | X | [8 empty] | X | X
Roads which have been authorized for private uses should remain available to those uses to the greatest extent possible. Any deterioration of the road should be repaired to a similar or better condition than before project activities occurred. |  | X | X | X |  | X |  |  | X | [7 empty] | X | X
Treatment units that already have off-road impacts and/or the potential for new and increased off-road vehicular use impacts are generally in areas that have a moderate or low slope angle (35% or less), and enough terrain to use the vehicle (four-wheel drive or all-terrain vehicles included). These areas will be protected from further encroachment of motorized vehicles by creating a buffer zone of no treatment or modification of treatment between the road, open for motorized travel, and the treatment area by installing fencing or other barriers made from natural materials (rock or wood). Buffer zones should be wide enough (minimum of 100 feet from edge of road) to discourage attempts at creating new routes. These areas will be identified with input from recreation staff and unit layout personnel prior to final unit boundary designation. | X |  |  | X |  | X |  |  | X | X |  |  |  |  | X
NRHP eligible sites located during the field inventory will have a 50 foot buffer established around the exterior boundary of the site. No construction activities will take place within the site and the 50 foot buffer area. | X |  |  | X |  |  |  |  | X | [6 empty] | X
All potentially ground-disturbing activities proposed for staging areas, road improvement, construction, or obliteration outside of planned treatment units will be intensively surveyed for cultural resources prior to project implementation. Any NRHP-eligible cultural resources will be avoided by project design. |  | X |  | X |  |  |  |  | X | [6 empty] | X
Consultation with Native American tribes must be completed prior to the closure of roads to ensure that access to areas of cultural importance is not inadvertently removed. | [5 empty] | X |  |  | X | [6 empty] | X |  | X

## Units
Unit Number | Vegetation Treatment | Treatment Method | Slash Treatment | Final GIS Acres | Final Unit Acres | Final Treatment Acres | Mechanical Acres | Manual Acres | Lpp PC/CC Treatable Acres | Mixed Conifer Acres | Aspen Acres | Meadow Acres | Regen. Acres | Est. Total Treatment Acres | Imp. Stage | Contract Type | Est. Ccf | Implementation Comments | Estimated Treatment Acres by Treatment Method | Estimated Number of Piles* | Hand (20/A) | Machine | Hand (25/A) | Hand (30/A)
1 | Lodgepole Pine Treatment | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 14.5084 | 15 | 4.5 |  | 4.4 | 4.3525 |  |  |  |  | 4.3525 | 1 | IDIQ |  |  | Manual: 4.5 | Hand: 90 | 90 | 0 | 113 | 135
2 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 49.0872 | 49 | 14.7 | 14.7 |  | 14.7262 |  |  |  |  | 14.7262 | 1 | IRSC | 75 |  | Mechanical: 14.7 | Machine: 3 | 0 | 3 | 0 | 0
3 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 30.7848 | 31 | 9.3 | 9.3 |  | 9.2354 |  |  |  |  | 9.2354 |  | IRSC | 46.1771 | Potential for additional regeneration thin aggregations. | Mechanical: 9.3 | Machine: 2 | 0 | 2 | 0 | 0
4 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 63.9334 | 64 | 19.2 | 19.2 |  | 19.18 |  |  |  |  | 19.18 |  | IRSC | 95.9001 |  | Mechanical: 19.2 | Machine: 3 | 0 | 3 | 0 | 0
5 | Aspen Restoration | Manual | chip and/or pile & burn | 16.6869 | 17 | 17 |  | 17 |  |  | 17 |  |  | 17 | 1 | IDIQ |  |  | Manual: 17 | Hand: 340 | 340 | 0 | 425 | 510
7 | Aspen Restoration | Manual | chip and/or pile & burn | 8.8979 | 9 | 9 |  | 9 |  |  | 9 |  |  | 9 | 1 | IDIQ |  |  | Manual: 9 | Hand: 180 | 180 | 0 | 225 | 270
8 | Aspen Restoration | Manual | chip and/or pile & burn | 6.7534 | 7 | 7 |  | 7 |  |  | 7 |  |  | 7 | 1 | IDIQ |  |  | Manual: 7 | Hand: 140 | 140 | 0 | 175 | 210
9 | Douglas-fir Mixed Conifer Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 155.6017 | 156 | 156 | 156 |  |  | 131 | 15 |  |  | 146 |  | IRSC | 365 | Approximately 10 ac will not be treated due to slope. | Mechanical: 156 | Machine: 23 | 0 | 23 | 0 | 0
10 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 28.0388 | 28 | 8.4 | 8.4 |  | 8.4116 |  |  |  |  | 8.4116 |  | IRSC | 42.0582 |  | Mechanical: 8.4 | Machine: 2 | 0 | 2 | 0 | 0
11 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 20.4198 | 20 | 6 | 6 |  | 6.126 |  |  |  |  | 6.126 |  | IRSC | 30.6298 | NW corner most likely location for patchcut/clearcut. | Mechanical: 6 | Machine: 1 | 0 | 1 | 0 | 0
12 | Douglas-fir Mixed Conifer Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 6.6969 | 7 | 7 | 7 |  |  | 6 |  |  |  | 6 |  | IRSC | 15 | 1 ac NW portion too steep; remote. No manual | Mechanical: 7 | Machine: 1 | 0 | 1 | 0 | 0
14 | Lodgepole Pine Treatment | Mechanical/ Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 34.8841 | 35 | 10.5 | 20.5 | 10 | 10.4652 |  | 10 | 10 |  | 30.4652 |  |  | 152.3262 | Aspen located in north and central part of unit. | Mechanical: 20.5 (10.5 LP CC/PC & 10 Aspen thin) Manual: 10 (Meadow thin) | Machine: 3 Hand: 200 | 200 | 3 | 250 | 315
15 | Aspen Restoration | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 21.0705 | 21 | 21 |  | 21 |  |  | 21 |  |  | 21 |  | IDIQ |  |  | Manual: 21 | Hand: 420 | 420 | 0 | 525 | 630
16 | Lodgepole Pine Treatment | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 26.2282 | 26 | 7.8 |  | 7.8 | 7.8685 |  |  |  |  | 7.8685 |  | IDIQ | 39.3423 |  | Manual: 7.8 | Hand: 156 | 156 | 0 | 195 | 234
17 | Lodgepole Pine Treatment | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 26.469 | 26 | 7.8 |  | 13.8 | 7.9407 |  | 3 |  | 5 | 15.9407 |  | IDIQ | 79.7035 | Aspen near NE. Possible meadow enhancement or regeneration thin from past entries. Recon during implementation (approximately 5-7 acres). Previously thinned in Winiger; apply appropriate % reduction and pile existing and activity fuels to an 10" diameter in regen portions as needed. | Manual: 13.8 (7.8 LP CC/PC & 3 Aspen thin & 3 Regen thin) | Hand: 276 | 276 | 0 | 345 | 414
18 | Meadow/Shrubland Restoration | Manual | chip and/or pile & burn | 8.3704 | 8 | 8 |  | 8 |  |  |  | 8 |  | 8 |  | IDIQ |  |  | Manual: 8 | Hand: 160 | 160 | 0 | 200 | 240
19 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 63.917 | 64 | 19.2 | 34.2 |  | 19.1751 |  | 15 |  |  | 34.1751 |  | IRSC | 170.8755 | Five pockets of aspen; arrange pc/cc near to aspen inclusions. | Mechanical: 34.2 (19.2 LP CC/PC & 15 Aspen thin) | Machine: 5 | 0 | 5 | 0 | 0
20 | Aspen Restoration | Mechanical/ Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 58.1169 | 58 | 58 | 31 | 27 |  |  | 31 |  |  | 31 |  |  |  | Mechanical in the northern half of the unit; manual in the southern half. | Mechanical: 31 Manual: 27 | Machine: 5 Hand: 540 | 540 | 5 | 675 | 810
21 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 27.2554 | 27 | 8.1 | 8.1 |  | 8.1766 |  | 27 |  |  | 35.1766 |  | IRSC | 175.8832 |  | Mechanical: 8.1 | Machine: 2 | 0 | 2 | 0 | 0
22 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 9.6512 | 10 | 3 | 3 |  | 2.8954 |  |  |  |  | 2.8954 |  | IRSC | 14.4768 |  | Mechanical: 3 | Machine: 1 | 0 | 1 | 0 | 0
23 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 21.0093 | 21 | 6.3 | 6.3 |  | 6.3028 |  |  |  |  | 6.3028 |  | IRSC | 31.514 |  | Mechanical: 6.3 | Machine: 1 | 0 | 1 | 0 | 0
24 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 16.3462 | 16 | 4.8 | 4.8 |  | 4.9039 |  |  |  |  | 4.9039 | 1 | IRSC | 25 |  | Mechanical: 4.8 | Machine: 1 | 0 | 1 | 0 | 0
26 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 121.7187 | 122 | 36.6 | 51.6 |  | 36.5156 |  | 15 |  |  | 51.5156 |  | IRSC | 257.5781 | Aspen in southwest and middle of unit to the northwest. | Mechanical: 51.6 (36.6 LP CC/PC & 15 Aspen thin) | Machine: 8 | 0 | 8 | 0 | 0
27 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 54.8434 | 55 | 16.5 | 21.5 |  | 16.453 |  | 5 |  |  | 21.453 |  | IRSC | 107.2651 | Aspen in southwest and eastern portion of unit; may have inclusions of mixed conifer on southern boundary. | Mechanical: 21.5 (16.5 LP CC/PC & 5 Aspen thin) | Machine: 4 | 0 | 4 | 0 | 0
28 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 109.1526 | 109 | 32.7 | 32.7 |  | 32.7458 |  |  |  |  | 32.7458 |  | IRSC | 163.7288 | Rock outcrops and steep slope in northeast portion of unit; maybe inclusions of mixed conifer. | Mechanical: 32.7 | Machine: 5 | 0 | 5 | 0 | 0
29 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 163.6944 | 164 | 49.2 | 59.2 |  | 49.1083 |  | 10 |  |  | 59.1083 |  | IRSC | 295.5416 | Interior Forest and LPP OG | Mechanical: 59.2 (49.2 LP CC/PC & 10 Aspen thin) | Machine: 9 | 0 | 9 | 0 | 0
30 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 13.8488 | 14 | 4.2 | 4.2 |  | 4.1547 |  |  |  |  | 4.1547 |  | IRSC | 20.7733 | Slope issues | Mechanical: 4.2 | Machine: 1 | 0 | 1 | 0 | 0
31 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 72.502 | 73 | 21.9 | 21.9 |  | 21.7506 |  |  |  |  | 21.7506 |  | IRSC | 108.753 | Slope issues | Mechanical: 21.9 | Machine: 4 | 0 | 4 | 0 | 0
39 | Douglas-fir Mixed Conifer Treatment | Mechanical/ Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 58.8647 | 59 | 59 | 45 | 14 |  | 48 | 3 | 8 |  | 59 |  |  | 147.5 | Some OG in unit. 42 acres mixed conifer mechanical; 6 acres mixed conifer manual. | Mechanical: 45 Manual: 14 | Machine: 7 Hand: 280 | 280 | 7 | 350 | 420
40 | Douglas-fir Mixed Conifer Treatment | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 105.7518 | 106 | 106 |  | 106 |  | 106 |  |  |  | 106 | 1 | IDIQ |  |  | Manual: 106 | Hand: 2,120 | 2120 | 0 | 2650 | 3180
41 | Meadow/Shrubland Restoration | Manual | chip and/or pile & burn | 28.9336 | 29 | 29 |  | 29 |  |  |  | 29 |  | 29 | 1 | IDIQ |  |  | Manual: 29 | Hand: 580 | 580 | 0 | 725 | 870
42 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 19.2577 | 19 | 5.7 | 11.7 |  | 5.7773 | 5 | 1 |  |  | 11.7773 |  |  | 58.8865 | Aspen in southern portion of unit. | Mechanical: 11.7 (5.7 LP CC/PC, 5 MC thin & 1 Aspen thin) | Machine: 2 | 0 | 2 | 0 | 0
43 | Douglas-fir Mixed Conifer Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 42.362 | 42 | 42 | 42 |  |  | 39 | 3 |  |  | 42 |  | IRSC | 105 | Aspen in southern and southwest portion of unit and in the middle of unit. | Mechanical: 42 | Machine: 6 | 0 | 6 | 0 | 0
45 | Douglas-fir Mixed Conifer Treatment | Mechanical/ Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 131.19 | 131 | 131 | 118 | 13 |  | 116 | 15 |  |  | 131 |  |  | 327.5 | Maunaul located in western portion of unit; portion between units 48 and 74. 103 acres mixed conifer mechanical; 13 acres mixed conifer manual. | Mechanical: 118 Manual: 13 | Machine: 17 Hand: 260 | 260 | 17 | 325 | 390
46 | Ponderosa Pine Mixed Conifer Treatment | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 11.5802 | 12 | 12 |  | 12 |  | 12 |  |  |  | 12 | 1 | IDIQ |  |  | Manual: 12 | Hand: 240 | 240 | 0 | 300 | 360
47 | Douglas-fir Mixed Conifer Treatment | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 20.0896 | 20 | 20 |  | 20 |  | 20 |  |  |  | 20 |  | IDIQ |  | Talk w/ Pinecliffe group about dropping the 300' buffer. | Manual: 20 | Hand: 400 | 400 | 0 | 500 | 600
48 | Ponderosa Pine Mixed Conifer Treatment | Mechanical/ Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 74.5128 | 75 | 75 | 62 | 13 |  | 52 | 7 |  |  | 59 |  |  | 147.5 | Recon - maybe an inclusion of lpp in northern portion. Combine manual on eastern portion of unit w/ manual portions of units 45 and 49. | Mechanical: 62 Manual: 13 | Machine: 9 Hand: 260 | 260 | 9 | 325 | 390
49 | Ponderosa Pine Mixed Conifer Treatment | Mechanical/ Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 47.4628 | 47 | 47 | 27 | 20 |  | 47 |  |  |  | 47 |  |  | 117.5 | Incorporate remaining mechanical treatment in unit 49 with unit 73 mechanical. Combine manual in western portion of unit w/ manual portion of unit 48. Change eastern portion of unit 49 to manual from mechanical up to unit 73. 27 acres mixed conifer mechanical; 20 acres mixed conifer manual. | Mechanical: 27 Manual: 20 | Machine: 4 Hand: 400 | 400 | 4 | 500 | 600
50 | Ponderosa Pine Mixed Conifer Treatment | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 6.8843 | 7 | 7 |  | 7 |  | 7 |  |  |  | 7 | 1 | IDIQ |  | Added back via letter from Miramonte LLC. | Manual: 7 | Hand: 140 | 140 | 0 | 175 | 210
51 | Ponderosa Pine Mixed Conifer Treatment | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 89.297 | 89 | 89 |  | 89 |  | 89 |  |  |  | 89 | 1 | IDIQ |  |  | Manual: 89 | Hand: 1,780 | 1780 | 0 | 2225 | 2670
52 | Ponderosa Pine Mixed Conifer Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 8.4179 | 8 | 8 | 8 |  |  | 10 |  |  |  | 10 |  | IRSC | 25 |  | Mechanical: 8 | Machine: 2 | 0 | 2 | 0 | 0
53 | Aspen Restoration | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 15.53 | 16 | 16 | 16 |  |  | 5 | 23 |  |  | 28 |  | IRSC |  | A couple pockets of mixed conifer/DF mixed into unit. | Mechanical: 16 | Machine: 3 | 0 | 3 | 0 | 0
54 | Mixed Conifer Treatment OG | Mechanical/ Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 18.012 | 18 | 18 | 13 | 5 |  | 18 |  |  |  | 18 |  |  |  | Combine manual portion w/ unit 80 manual. 13 acres mixed conifer mechanical; 5 acres mixed conifer manual. | Mechanical: 13 Manual: 5 | Machine: 2 Hand: 100 | 100 | 2 | 125 | 150
55 | Douglas-fir Mixed Conifer Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 5.3421 | 5 | 5 | 5 |  |  | 5 |  |  |  | 5 |  | IRSC |  |  | Mechanical: 5 | Machine: 2 | 0 | 2 | 0 | 0
58 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 25.7316 | 26 | 7.8 | 7.8 |  | 7.8 |  |  |  |  | 7.8 |  | IRSC | 39 |  | Mechanical: 7.8 | Machine: 2 | 0 | 2 | 0 | 0
59 | Douglas-fir Mixed Conifer Treatment | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 14.43 | 14 | 14 |  | 14 |  | 9 | 4 |  | 2 | 15 |  | IDIQ |  | Previously thinned in Winiger; apply appropriate % reduction and pile existing and activity fuels to a 10" diameter. | Manual: 14 | Hand: 280 | 280 | 0 | 350 | 420
60 | Douglas-fir Mixed Conifer Treatment | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 4.6665 | 5 | 5 |  | 5 |  | 10 |  |  |  | 10 |  | IDIQ |  | Previously thinned in Winiger; apply appropriate % reduction and pile existing and activity fuels to a 10" diameter. | Manual: 5 | Hand: 100 | 100 | 0 | 125 | 150
61 | Aspen Restoration | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 6.7114 | 7 | 7 | 7 |  |  |  | 7 |  |  | 7 |  | IRSC |  |  | Mechanical: 7 | Machine: 1 | 0 | 1 | 0 | 0
63 | Ponderosa Pine Mixed Conifer Treatment | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 5.1889 | 5 | 5 |  | 5 |  | 5 |  |  |  | 5 | 1 | IDIQ |  |  | Manual: 5 | Hand: 100 | 100 | 0 | 125 | 150
67 | Aspen Restoration | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 12.5285 | 13 | 13 | 13 |  |  |  | 13 |  |  | 13 |  | IRSC |  |  | Mechanical: 13 | Machine: 2 | 0 | 2 | 0 | 0
68 | Douglas-fir Mixed Conifer Treatment | Mechanical/ Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 10.0541 | 10 | 10 | 7 | 3 |  | 10 |  |  |  | 10 |  |  | 25 | 7 acres mixed conifer mechanical; 3 acres mixed conifer manual. | Mechanical: 7 Manual: 3 | Machine: 1 Hand: 60 | 60 | 1 | 75 | 90
73 | Ponderosa Pine Mixed Conifer Treatment | Mechanical/ Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 75.529 | 76 | 76 | 65 | 11 |  | 76 |  |  |  | 76 |  |  | 190 | 65 acres mixed conifer mechanical; 11 acres mixed conifer manual. | Mechanical: 65 Manual: 11 | Machine: 10 Hand: 220 | 220 | 10 | 275 | 330
74 | 2-Staged Mixed Conifer Treatment | Manual | 1) pile & burn 2) thin and pile & burn | 43.8452 | 44 | 44 |  | 44 |  | 44 |  |  |  | 44 | 1 | IDIQ |  | Two-staged treatment: 1) Piling only; 2) 40% BA cut and pile. | Manual: 44 | Hand: 880 | 880 | 0 | 1100 | 1320
75 | Lodgepole Pine Treatment | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 14.4328 | 14 | 4.2 |  | 4.2 | 4.3299 |  | 2 |  |  | 6.3299 |  | IDIQ | 31.6493 | Aspen in eastern potion of unit; mixed conifer in western portion. | Manual: 4.2 | Hand: 84 | 84 | 0 | 105 | 126
76 | Lodgepole Pine Treatment | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 11.9941 | 12 | 3.6 |  | 7.6 | 3.5982 | 4 |  |  |  | 7.5982 |  | IDIQ | 37.9912 | Mixed conifer in souther portion of unit. | Manual: 7.6 (3.6 LP CC/PC & 4 MC thin) | Hand: 152 | 152 | 0 | 190 | 228
77 | Douglas-fir Mixed Conifer Treatment | Mechanical/ Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 268.9453 | 269 | 269 | 239 | 30 |  | 209 | 30 |  |  | 239 |  |  | 597.5 | Interior Forest aggregations in east portion. Manual in southern portion of unit due to accessability and rock. About 209 acres mixed conifer mechanical; 30 acres mixed conifer manual. | Mechanical: 239 Manual: 30 | Machine: 35 Hand: 600 | 600 | 35 | 750 | 900
80 | Douglas-fir Mixed Conifer Treatment | Mechanical/ Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 8.0925 | 8 | 8 | 7 | 1 |  | 8 |  |  |  | 8 |  |  | 20 | Manual portion combine w/ unit 54 manual. 7 acres mixed conifer mechanical; 1 acre mixed conifer manual. | Mechanical: 7 Manual: 1 | Machine: 1 Hand: 20 | 20 | 1 | 25 | 30
81 | Aspen Restoration | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 12.2503 | 12 | 12 | 12 |  |  |  | 12 |  |  | 12 |  | IRSC |  |  | Mechanical: 12 | Machine: 2 | 0 | 2 | 0 | 0
82 | Regeneration Thin | Manual | chip and/or pile & burn | 1.2487 | 1 | 1 |  | 1.2487 |  |  |  |  | 1.2487 | 1.2487 | 1 | IDIQ |  |  | Manual: 1 | Hand: 20 | 20 | 0 | 25 | 30
83 | Regeneration Thin | Manual | chip and/or pile & burn | 0.36095 | 0.4 | 0.4 |  | 0.36095 |  |  |  |  | 0.36095 | 0.36095 | 1 | IDIQ |  |  | Manual: 0.4 | Hand: 8 | 8 | 0 | 10 | 12
84 | Regeneration Thin within Defensible Space | Manual | chip and/or pile & burn | 0.28 | 0.3 | 0.3 |  | 0.28 |  |  |  |  | 0.28 | 0.28 | 1 | IDIQ |  | Unit in 300' no-cut boundary to be included per decision. | Manual: 0.3 | Hand: 6 | 6 | 0 | 8 | 9
85 | Regeneration Thin | Manual | chip and/or pile & burn | 0.63084 | 1 | 1 |  | 0.63084 |  |  |  |  | 0.63084 | 0.63084 | 1 | IDIQ |  |  | Manual: 1 | Hand: 20 | 20 | 0 | 25 | 30
86 | Regeneration Thin | Manual | chip and/or pile & burn | 0.54541 | 1 | 1 |  | 0.54541 |  |  |  |  | 0.54541 | 0.54541 | 1 | IDIQ |  |  | Manual: 1 | Hand: 20 | 20 | 0 | 25 | 30
87 | Regeneration Thin within Defensible Space | Manual | chip and/or pile & burn | 0.46 | 0.5 | 0.5 |  | 0.46 |  |  |  |  | 0.46 | 0.46 | 1 | IDIQ |  | Unit in 300' no-cut boundary to be included per decision. | Manual: 0.5 | Hand: 10 | 10 | 0 | 13 | 15
88 | Regeneration Thin within Defensible Space | Manual | chip and/or pile & burn | 0.36 | 0.4 | 0.4 |  | 0.36 |  |  |  |  | 0.36 | 0.36 | 1 | IDIQ |  | Unit in 300' no-cut boundary to be included per decision. | Manual: 0.4 | Hand: 8 | 8 | 0 | 10 | 12
89 | Regeneration Thin | Manual | chip and/or pile & burn | 0.7676 | 1 | 1 |  | 0.7676 |  |  |  |  | 0.7676 | 0.7676 | 1 | IDIQ |  |  | Manual: 1 | Hand: 20 | 20 | 0 | 25 | 30
90 | Regeneration Thin | Manual | chip and/or pile & burn | 0.53432 | 0.5 | 0.5 |  | 0.53432 |  |  |  |  | 0.53432 | 0.53432 | 1 | IDIQ |  | Portion in 300' no-cut boundary to be included per decision. | Manual: 0.5 | Hand: 8 | 10 | 0 | 12.5 | 15
91 | Regeneration Thin within Defensible Space | Manual | chip and/or pile & burn | 0.57 | 0.6 | 0.6 |  | 0.57 |  |  |  |  | 0.57 | 0.57 | 1 | IDIQ |  | Unit in 300' no-cut boundary to be included per decision. | Manual: 0.6 | Hand: 12 | 12 | 0 | 15 | 18
92 | Regeneration Thin | Manual | chip and/or pile & burn | 0.51786 | 0.5 | 0.5 |  | 0.51786 |  |  |  |  | 0.51786 | 0.51786 | 1 | IDIQ |  | Portion in 300' no-cut boundary to be included per decision. | Manual: 0.5 | Hand: 8 | 10 | 0 | 12.5 | 15
93 | Regeneration Thin | Manual | chip and/or pile & burn | 0.47872 | 0.5 | 0.5 |  | 0.47872 |  |  |  |  | 0.47872 | 0.47872 | 1 | IDIQ |  |  | Manual: 0.5 | Hand: 10 | 10 | 0 | 13 | 15
94 | Regeneration Thin | Manual | chip and/or pile & burn | 0.5302 | 1 | 1 |  | 0.5302 |  |  |  |  | 0.5302 | 0.5302 | 1 | IDIQ |  |  | Manual: 1 | Hand: 20 | 20 | 0 | 25 | 30
95 | Regeneration Thin | Manual | chip and/or pile & burn | 0.43296 | 0.4 | 0.4 |  | 0.43296 |  |  |  |  | 0.43296 | 0.43296 | 1 | IDIQ |  |  | Manual: 0.4 | Hand: 8 | 8 | 0 | 10 | 12
96 | Regeneration Thin | Manual | chip and/or pile & burn | 2.0021 | 2 | 2 |  | 2.0021 |  |  |  |  | 2.0021 | 2.0021 | 1 | IDIQ |  |  | Manual: 2 | Hand: 40 | 40 | 0 | 50 | 60
97 | Regeneration Thin | Manual | chip and/or pile & burn | 1.4171 | 1 | 1 |  | 1.4171 |  |  |  |  | 1.4171 | 1.4171 | 1 | IDIQ |  |  | Manual: 1 | Hand: 20 | 20 | 0 | 25 | 30
98 | Regeneration Thin | Manual | chip and/or pile & burn | 0.32232 | 0.3 | 0.3 |  | 0.32232 |  |  |  |  | 0.32232 | 0.32232 | 1 | IDIQ |  |  | Manual: 0.3 | Hand: 6 | 6 | 0 | 8 | 9
99 | Regeneration Thin | Manual | chip and/or pile & burn | 2.4743 | 2 | 2 |  | 2.4743 |  |  |  |  | 2.4743 | 2.4743 | 1 | IDIQ |  |  | Manual: 2 | Hand: 40 | 40 | 0 | 50 | 60
100 | Regeneration Thin | Manual | chip and/or pile & burn | 0.5288 | 0.5 | 0.5 |  | 0.5288 |  |  |  |  | 0.5288 | 0.5288 |  | IDIQ |  | Portion in 300' no-cut boundary to be included per decision. | Manual: 0.5 | Hand: 4 | 10 | 0 | 12.5 | 15
101 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 38.852 | 39 | 11.7 | 15.7 |  | 11.6556 |  | 4 |  |  | 15.6556 |  | IRSC | 78.2779 |  | Mechanical: 15.7 (11.7 LP CC/PC & 4 Aspen thin) | Machine: 3 | 0 | 3 | 0 | 0
102 | Aspen Restoration | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 10.6978 | 11 | 11 | 11 |  |  |  | 11 |  |  | 11 |  | IRSC |  |  | Mechanical: 11 | Machine: 2 | 0 | 2 | 0 | 0
103 | Lodgepole Pine Treatment | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 19.5814 | 20 | 6 | 9 |  | 5.8744 |  | 3 |  |  | 8.8744 |  | IRSC | 44.372 | Locate clearcut in center of unit between aspen inclusions. | Mechanical: 9 (6 LP CC/PC & 3 Aspen thin) | Machine: 2 | 0 | 2 | 0 | 0
104 | Ponderosa Pine Mixed Conifer Treatment | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 7.834 | 8 | 8 |  | 8 |  | 8 |  |  |  | 8 |  | IDIQ |  | Previously thinned in Winiger; apply appropriate % reduction and pile existing and activity fuels to a 10" diameter. | Manual: 8 | Hand: 160 | 160 | 0 | 200 | 240
105 | Ponderosa Pine Mixed Conifer Treatment | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 12.3729 | 12 | 12 |  | 12 |  | 8 | 2 | 2 |  | 12 |  | IDIQ |  |  | Manual: 12 | Hand: 240 | 240 | 0 | 300 | 360
106 | Aspen Restoration | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 18.3446 | 18 | 18 | 18 |  |  |  | 18 |  |  | 18 |  | IRSC |  |  | Mechanical: 18 | Machine: 3 | 0 | 3 | 0 | 0
107 | Lodgepole Pine Treatment | Manual | Summary | 4.752 | 5 | 1.5 |  | 3.5 | 1.4256 |  | 2 |  |  | 3.4256 | 1 | IDIQ |  |  | Manual: 3.5 (1.5 LP CC/PC & 2 Aspen thin) | Hand: 70 | 70 | 0 | 88 | 105
*Based on 20 hand piles/acre cut and 1 machine pile/3.33 acres cut of mixed conifer cut and 1 machine pile/1 acre of LP cut |  |  | Total Acres | 2575.2732 | 2577.9 | 1805.1 | 1278.8 | 615.7623 | 330.9489 | 1107 | 345 | 57 | 21.4623 | 1861.4111 |  |  | 4305.2035 |  | Total Estimated Machine Piles | 202 |  | 202
|  | Final Total Defensible Space Acres |  |  | 2187 | 2187 | [12 empty] | Total Estimated Hand Piles | 12326 | 12326 |  | 15410.5 | 18504
|  | Final Total Broadcast Burn Acres |  |  | 945 | 945
| Row Labels | Sum of Unit Acres | Sum of Treatment Acres
| 2-Staged Mixed Conifer Treatment | 44 | 44 | [9 empty] | Stage 1 | 246.0459
| Aspen Restoration | 189 | 189 | [9 empty] | Stage 2
| Lodgepole Pine Treatment | 1104 | 331.2 | [9 empty] | Stage 3
| Meadow/Shrubland Restoration | 37 | 37 | [9 empty] | Stage 4
| Regeneration Thin | 12.6 | 12.6 | [9 empty] | Stage 5
| Mixed Conifer Treatment OG | 18 | 18
| Douglas-fir Mixed Conifer Treatment | 832 | 832
| Ponderosa Pine Mixed Conifer Treatment | 339 | 339
| Regeneration Thin within Defensible Space | 2.3 | 2.3
| Grand Total | 2577.9 | 1805.1