**Forsythe II Multiparty Monitoring Group Timeline for Contracts**

|  |  |  |
| --- | --- | --- |
| **Date** | **Event or Action** | **Notes** |
| **2018** | | |
| **February 28, 2018** | **Deadline to submit Phase 1 Avenza .klm files to Jim Cowart (**[**jimcowart@gmail.com**](mailto:jimcowart@gmail.com)**)** | **Jim Cowart will be compiling Phase 1 Avenza .klm files for March 14th meeting** |
| March 14, 2018 | **MMG meeting --** discuss Phase 1 Avenza data collected by MMG | MMG will collaborate on important Phase 1 input to provide to USFS by March 30, 2018 |
| Week of March 18th | DAT Field Trip Units 1&2 | DAT/USFS Field Review of proposal. |
| **March 30, 2018** | **Final deadline to submit MMG Phase 1 input to USFS** | **Input will be in spatial format (shapefiles) as well as a written document of explanation if deemed appropriate by MMG** |
| Week of April 2 | GTR Webinar |  |
| April 6, 2018 | Completed and analysis surveys to MMG |  |
| April 16, 2018 | **MMG meeting –** Discuss Resource Surveys |  |
| April 27, 2018 | Phase 1 Rx and Step Transects to MMG |  |
| **May 7, 2018** | **Deadline to submit Phase 2 Avenza .klm files to Jim Cowart (?) (**[**jimcowart@gmail.com**](mailto:jimcowart@gmail.com)**)** | **Jim (?) will be compiling Phase 2 Avenza .klm files for May 21st meeting** |
| May 16, 2018 | **Phase 1 Rx and Step Transect comments from MMG to USFS** |  |
| May 21, 2018 | **MMG meeting** -- discuss Phase 2 Avenza data collected by MMG  Discuss Phase 1 Rx and Step Transects. | MMG will collaborate on important Phase 2 input to provide to USFS by June 1, 2018 |
| **June 1, 2018** | **Final deadline to submit MMG Phase 2 input to USFS** | **Input will be in spatial format (shapefiles) as well as a written document of explanation if deemed appropriate by MMG** |
| June 20, 2018 | **MMG meeting** -- TBD |  |
| June 29, 2018 | Phase 1 layout prep completed | Step transects, boundary flagging and painting, tree marking, and cruising of Phase 1 units completed by USFS. |
| Week of July 9 | Field Trip | Visit some of Phase 1 units and USFS will address questions about the prep and layout. |
| July 20, 2018 | Phase 2 Rx and Step Transects to MMG |  |
| Week of July 30 | Field Trip – Review sample of Phase 2 units. |  |
| July 31, 2018 | **Phase 1 layout prep comments from MMG to USFS** |  |
| Week of August 13 | MMG meeting – Discuss Phase 1 Layout Prep Field Final Work |  |
| August 17, 2018 | **Phase 2 Rx and Step Transect comments from MMG to USFS** |  |
| August 31, 2018 | Field Surveys completed Phases 1 &2 |  |
| September 4, 2018 | Phase 3 and Phase 4 units identified by USFS | USFS will determine units to be completed during Phase 3 and 4. |
| Week of September 3 | **MMG meeting** -- TBD |  |
| September 14, 2018 | Phase 2 layout prep completed | Boundary flagging and painting, tree marking, and cruising of Phase 2 units completed by USFS. |
| Week of September 24 | Field Trip | Visit some of Phase 2 units and USFS will address questions about the prep and layout. |
| October 12, 2018 | **Phase 2**  **layout prep comments from MMG to USFS** |  |
| October 11, 2018 | MMG meeting |  |
| October 26, 2018 | Phase 2 layout and prep completed | Boundary flagging and cruising for Phase 2 units completed by USFS. The painting of unit boundaries will not be completed until Spring 2019. |
| November 9, 2018 | Phase 1 Layout and prep completed | Boundary flagging, tree marking for Phase 1 completed by USFS. Cruising remains will be completed by end of November. |
| November 19, 2018 | MMG meeting - Review Timeline; Monitoring priorities |  |
| December 5, 2018 | MMG meeting -- TBD | Cancelled – Gov. closed (George H. Bush memorial) |
| December 21, 2018 | Phase 1 Contract Draft sent to MMG for review | This is the USFS release date of the Phase 1 contract |
|  | | |
| **Date** | **Event of Action** | **Notes** |
| **2019** | | |
| January 9, 2019 | MMG meeting -- TBD | Discuss Phase 1 contract  Cancelled – Gov. Furlough |
| **January 18, 2019** | **MMG Deadline** | **MMG Contract review period ends for Phase 1. Postponed – Gov. Furlough** |
| **January 25, 2019** | **USFS Deadline** | **This is the USFS release date of the Phase 2 contract. Phase 2 Contract submitted to Contracting Officer for review. Phase 2 Contract Draft sent to MMG for review**  **Postponed – Gov. Furlough** |
| **January 31, 2019** | **USFS Deadline** | **Phase 1 contract submitted to Acquisition Management. Acquisition Management processes the contract after the receipt of contract. Postponed due to Gov. Furlough.** |
| **February 8, 2019** | **MMG Deadline** | **MMG Contract review period ends for Phase 2. Postponed due to Gov. Furlough.** |
| February 25, 2019 | MMG Meeting | Phases 1&2 Update; Timeline for Phase 3; Slash piles; TWI maps; Prepping for monitoring |
| **February 28, 2019** | **USFS Deadline** | **Phase 2 contract submitted to USFS Acquisition Management. Postponed due to Gov. Furlough.** |
| **March 1, 2019** | **MMG Deadline** | **Last day to submit Phase 3 and Phase 4 Avenza points. Extended until May 12, 2019 due to snow and timing of discussion.** |
| March 7, 2019 | Information | Timeline, Master Stand List Update, and Draft Phase 2 contract on website |
| March 13, 2019 | MMG Meeting | Discuss units 3, 4, 63, & 107; Phase 2 Contract Q & A. **Cancelled due to blizzard.** |
| **February 22, 2019**  **(Past Due)** | **USFS Deadline** | **Phase 1 contract submitted to Acquisition Management.** |
| **April 5, 2019** | **USFS Deadline** | **Phase 2 contract submitted to Acquisition Management.** |
| April 10, 2019 | MMG Meeting | Reschedule to April 15 due to inclement weather. |
| May 8, 2019 | MMG Meeting | Mixed conifer and ponderosa pine units discussion |
| **May 12, 2019** | **MMG Deadline** | **Last day to submit Phase 3 and Phase 4 Avenza points.**  **(Some Avenza points received)**  **Final deadline extended until June 30, 2019 to provide more time while continuing the landscape scale discussion.** |
| June 20, 2019 | Information | Phase 1 Contract Awarded. Estimated start date TBD. |
| June 22, 2019 | MMG Field Trip | Field trip to mixed conifer unit(s) |
| **June 30, 2019** | **MMG Deadline** | **Final deadline to submit Avenza points for Phases 3 & 4.** |
| July 22, 2019 | MMG Meeting | Lodgepole pine units discussion |
| July 26, 2019 | Information | Phases 3 & 4 Step transects completed[[1]](#footnote-1)  *Note: Date extended as field crews did not start until mid-June.* |
| August 9, 2019 | Information | Estimated Phase 2 Contract Award. Estimated start date would be within a month of contract award. |
| August 14, 2019 | MMG Field Trip | Field trip to lodgepole pine unit(s) |
| September 6, 2019 | Information | Phase 5 and Phase 6 units identified. |
| September 11, 2019 | MMG Meeting | Wildlife considerations |
| September 14, 2019 | MMG Field Trip | Field trip to key unit(s) for wildlife considerations |
| **October 15, 2019** | **MMG Deadline** | **Final field input (e.g. tree mark, treatment activities, etc.) for Phases 3 & 4 input from MMG to USFS.** |
| October 9, 2019 | MMG Meeting | Unit specific discussions |
| **November 8, 2019** | **USFS Deadline** | **Phase 3 &4 layout prep completed. USFS will complete flag, paint, and mark trees, and cruise in Phases 3 & 4 units.** |
| November 18, 2019 | Information | Draft Phases 3 and 4 contracts out for review by MMG. |
| November 20, 2019 | MMG Meeting | Unit specific discussions |
| **December 2, 2019** | **MMG Deadline** | **MMG Contract review period ends for Phases 3 and 4.** |
| December 13, 2019 | Information | Phases 3 & 4 Contracts submitted to Contracting Officer for review. |
| December 18, 2019 | MMG Meeting | Discuss Phase 3 & 4 contract packages to be submitted to AQM. |
|  | | |
| **Date** | **Event or Action** | **Notes** |
| **2020** | | |
| January, 2020 | MMG Meeting | TBD |
| January 15, 2020 | Information | Phase 3 &4 Contract adjustments from Contracting officer. |
| **January 24, 2020** | **USFS Deadline** | **Phase 3 and Phase 4 Contracts submitted to Acquisition Management.** |
| February, 2020 | MMG Meeting | TBD |
| March, 2020 | MMG Meeting | TBD |
| April, 2020 | MMG Meeting | TBD |
| **April 24, 2020** | **MMG Deadline** | **Final deadline to submit Avenza points for Phases 5 & 6.** |

Manual contracts are identified with odd numbers (i.e. Phase1 & 3), and mechanical contracts with even numbers (i.e. Phase 2 & 4).

1. Units to be treated in Phases 3 and 4 have not been finalized. Crews will be doing field work in units generally anticipated to be treated in Phases 3 and 4 while we continue the landscape scale discussion. [↑](#footnote-ref-1)