## Sheet1
FORSYTHE II
All Units
Unit Number | Vegetation Treatment | Phase | Unit Acres | Treatment Acres | GPS Acres | Treatment Method | Slash Treatment | Step Transect Completed | Existing Basal Area (ft 2 / ac) | Desired Basal Area Range (ft 2 / ac) | Unit Boundary Flagged | Unit Boundary Painted | Draft Rx | Sample Mark Completed | Final Rx | Tree Marking Completed | Cruise Method Used | Cruise Completed | Crosswalk Review | Unit Maps Completed | Appraisal Completed | Timber Sale Report | Contract Package Draft | MMG Contract Review | Contract Officer Review | Contract to AQM | Contract Awarded | Contract Started | Contract Completed | Post Step Transect Completed | Unit Changes Notification | Pile Burning Completed | Comments
1 | Lodgepole Pine Treatment |  | 15 | 4.5 | 6.3 | Manual | Chip and/or pile & burn | 2018-07-10 | 96 |  | 2018-08-29 | [5 empty] | Fix 1/50th | 2018-11-01 | [14 empty] | 4.2 acres of patchcut; 4.5 acres of aspen aggregations; Unit delayed - decision by Angie 3/13/2019
2 | Lodgepole Pine Treatment |  | 49 | 14.7 | 4.5 | Manual | Chip and/or pile & burn | 2018-07-10 | 119 |  | 2018-09-05 | [5 empty] | Fix 1/50th | 2018-11-01 | [14 empty] | Removed from Phase II Mechanical to Phase 1 Manual 6/14/2018; Unit delayed - decision by Angie 3/13/2019
3 | Lodgepole Pine Treatment |  | 31 | 9.3 | 7.4 | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2018-07-10 | 100 |  | 2018-08-27 |  | 2018-10-02 |  |  |  | Fix 1/50th | 2018-11-01 |  | 2018-12-21 |  |  | 2018-12-21 | 2019-01-29 | NA | [7 empty] | Removed from Phase II Mechanical to Phase 1 Manual 8/27/2018; DF Mixed Conifer Aggregation sample mark completed; Aggregation needs to be painted. Aggregation marked. Unit delayed - decision by Angie 3/13/2019
4 | Lodgepole Pine Treatment |  | 64 | 19.2 | 11.5 | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2018-07-10 | 100 |  | 2018-08-28 |  | 2018-11-02 | 2018-10-05 |  | 2018-11-06 | Fix 1/50th | 2018-11-01 |  | 2018-12-21 |  |  | 2018-12-21 | 2019-01-29 | NA | [7 empty] | Removed from Phase II Mechanical to Phase 1 Manual 8/27/2018; DF Mixed Conifer Aggregation sample mark completed; Aggregation needs to be painted. Aggregation marked. Unit delayed - decision by Angie 3/13/2019
5 | Aspen Restoration | 1 | 17 | 17 | 17 | Manual | Chip and/or pile & burn | NA |  |  | 2018-10-25 | NA | 2017-12-05 | NA |  | NA | Fix 1/20th | 2018-02-12 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-02-24 | Unit was identified as flagged on 12/5/2017; not fully completed
7 | Aspen Restoration | 1 | 9 | 9 | 8 | Manual | Chip and/or pile & burn | NA |  |  | 2018-10-25 | NA | 2017-12-05 | NA |  | NA | Fix 1/20th | 2018-02-12 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-02-24 | Unit was identified as flagged on 12/5/2017; not fully completed
8 | Aspen Restoration | 1 | 7 | 7 | 6 | Manual | Chip and/or pile & burn | NA |  |  | 2018-10-25 | NA | 2017-12-05 | NA |  | NA | Fix 1/20th | 2018-02-12 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-02-24 | Unit was identified as flagged on 12/5/2017; not fully completed
9 | Douglas-fir Mixed Conifer Treatment | 4 | 156 | 156 | 46 | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-09-13 | 84 | 50-54 | 2019-09-17 | 2019-09-24 |  | None |  | 2019-10-17 | Fix 1/50th | 2019-11-20 |  | 2019-10-31 | 2019-12-17 | 2019-12-17 | 2020-12-22 | 2020-02-19 | 2020-02-28 | 2020-03-06 | 2020-07-21 | [5 empty] | Blue Dot Contract
9 | Douglas-fir Mixed Conifer Treatment | 3 | 156 | 156 | 58 | Manual | Chip and/or pile & burn | 2019-09-13 | 84 | 60-65 | 2019-09-07 | NA |  | 2019-09-04 |  | 2019-09-30 | Fix 1/20th | 2019-11-20 |  | 2019-12-11 | NA | NA | 2019-11-15 | 2020-01-24 | NA | 2020-01-29 | 2020-06-03 | 2021-06-17 | 2021-07-21 | 2021-08-03
9 | Douglas-fir Mixed Conifer Treatment |  |  | `25 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-09-13 | 84
9 | Douglas-fir Mixed Conifer Treatment |  |  | `25 |  | Manual | Chip and/or pile & burn | 2019-09-13 | 84
10 | Lodgepole Pine Treatment | 4 | 28 | 8.4 | 4 | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-09-13 | 128 | Patchcut | 2019-09-18 | 2019-10-28 |  | None |  | NA | Fix 1/50th | 2019-11-20 |  | 2019-10-31 | 2019-12-17 | 2019-12-17 | 2020-12-22 | 2020-02-19 | 2020-02-28 | 2020-03-06 | 2020-07-21 | [5 empty] | Blue Dot Contract
11 | Lodgepole Pine Treatment |  | 20 | 6 | 2 | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-09-13 | 119 |  | 2019-09-18 | NA |  |  |  | NA | Fix 1/50th | 2019-11-20 | [14 empty] | Unit dropped
12 | Douglas-fir Mixed Conifer Treatment |  | 7 | 7 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-09-13 | 171
14 | Lodgepole Pine Treatment |  | 35 | 10.5 |  | Mechanical/ Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-07-10 | 78
15 | Aspen Restoration |  | 21 | 21 |  | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-07-10 | 40
16 | Lodgepole Pine Treatment |  | 26 | 7.8 |  | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-07-09 | 93
17 | Lodgepole Pine Treatment |  | 26 | 7.8 |  | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-07-10 | 105
18 | Meadow/Shrubland Restoration |  | 8 | 8 |  | Manual | chip and/or pile & burn | 2019-07-10 | 16
19 | Lodgepole Pine Treatment |  | 64 | 19.2 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-07-08 | 93
20 | Aspen Restoration | 3 | 58 | 58 | 62 | Manual | Chip and/or pile & burn or lop/scatter | 2019-09-13 | 73 |  | 2019-10-24 | NA |  | None |  | NA | Fix 1/20th | 2019-11-18 |  | 2019-12-11 | NA | NA | 2019-11-15 | 2020-01-24 | NA | 2020-01-29 | 2020-06-03 | 2021-06-17 | 2021-07-21 | 2021-08-03
21 | Lodgepole Pine Treatment |  | 27 | 8.1 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-07-18 | 163
22 | Lodgepole Pine Treatment |  | 10 | 3 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-07-09 | 116
23 | Lodgepole Pine Treatment | 5 | 21 | 6.3 | 6 | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-07-09 | 120 | Various Treatments | 2020-08-11 | NA |  | None |  | 2020-08-18 | Fix 1/20th; Fix 1/50th | 2020-10-27 |  | 2020-12-07 | NA | NA | 2020-12-07 | 2020-12-16 | NA | 2021-01-15 | [6 empty] | Combination thin, patchcuts, and surface fuels
24 | Lodgepole Pine Treatment | 5 | 16 | 4.8 | 4 | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2018-07-10 | 82 | Patchcuts | 2020-08-11 | NA |  | None |  | NA | Fix 1/50th | 2020-10-27 |  | 2020-12-07 | NA | NA | 2020-12-07 | 2020-12-16 | NA | 2021-01-15 | [6 empty] | 3/5/2019: The MMG and Contract Officer reviews will be occurring simultaneously due to contract deadlines established by AQM; Unit delayed - decision by Angie 3/13/2019; Put into Phase 5
26 | Lodgepole Pine Treatment | 1 | 122 | 36.6 | 6.6 | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2018-07-10 | 88 | Patchcuts | 2018-10-12 | NA |  | NA |  | NA | Fix 1/50th | 2018-11-05 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-02-25 | Unit was identified as flagged on 8/1/2018; not fully completed. Flagging completed 10/12/2018.
26 | Lodgepole Pine Treatment | 2 | 122 | 36.6 | 4.6 | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2018-07-10 | 88 | Patchcuts | 2018-10-12 |  |  | NA |  | NA | Fix 1/50th | 2018-11-05 | Completed | 2019-01-14 | 2019-02-28 | 2019-02-28 | 2019-02-25 | 2019-02-08 | 2019-01-25 | 2019-02-28 | 2020-08-11 | 2021-02-18 | 2021-04-27 |  |  |  | Unit was identified as flagged on 8/1/2018; not fully completed. Flagging completed 10/12/2018. The MMG and Contract Officer reviews will be occurring simultaneously due to contract deadlines established by AQM. Manchester Contract
27 | Lodgepole Pine Treatment | 2 | 55 | 16.5 | 10 | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2018-07-10 | 83 | Patchcuts | 2018-10-17 |  |  | NA |  | NA | Fix 1/50th | 2018-11-05 | Completed | 2019-01-14 | 2019-02-28 | 2019-02-28 | 2019-02-25 | 2019-02-08 | 2019-01-25 | 2019-02-28 | 2020-08-11 | 2021-02-18 | 2021-04-27 |  |  |  | Unit was identified as flagged on 8/1/2018; not fully completed. Flagging completed 10/17/2018. 3/5/2019: The MMG and Contract Officer reviews will be occurring simultaneously due to contract deadlines established by AQM. Manchester Contract
28 | Lodgepole Pine Treatment | 2 | 109 | 32.7 | 35 | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2018-07-10 | 83 | Patchcuts | 2018-10-19 |  |  | NA |  | NA | Fix 1/50th | 2018-11-05 | Completed | 2019-01-14 | 2019-02-28 | 2019-02-28 | 2019-02-25 | 2019-02-08 | 2019-01-25 | 2019-02-28 | 2020-08-11 | 2021-02-18 | 2021-04-27 |  |  |  | Unit was identified as flagged on 8/1/2018; not fully completed. Flagging completed 10/19/2018. 3/5/2019: The MMG and Contract Officer reviews will be occurring simultaneously due to contract deadlines established by AQM. Manchester Contract
29 | Lodgepole Pine Treatment | 5 | 164 | 49.2 | 43 | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-09-13 | 101 | Various Treatments | 2020-08-14 | NA |  | None |  | 2020-08-28 | Fix 1/20th; Fix 1/50th | 2020-10-27 |  | 2020-12-07 | NA | NA | 2020-12-07 | 2020-12-16 | NA | 2021-01-15 | [6 empty] | Combination thin, patchcuts, and surface fuels
30 | Lodgepole Pine Treatment | 5 | 14 | 4.2 | 1 | Manual | Chip and/or pile & burn | 2019-09-13 | 62 | Patchcuts | 2020-07-30 | NA |  | None |  | NA | Fix 1/50th | 2020-10-27 |  | 2020-12-07 | NA | NA | 2020-12-07 | 2020-12-16 | NA | 2021-01-15
31 | Lodgepole Pine Treatment | 5 | 73 | 21.9 | 18 | Manual | Chip and/or pile & burn | 2019-09-13 | 47 | Patchcuts | 2020-07-30 | NA |  | None |  | NA | Fix 1/50th | 2020-10-27 |  | 2020-12-07 | NA | NA | 2020-12-07 | 2020-12-16 | NA | 2021-01-15
38 | Broadcast Burn |  | 747 | 747 |  | Broadcast Burn | Prescribed Broadcast Burn
39 | Douglas-fir Mixed Conifer Treatment | 1 | 59 | 59 | 36 | Manual | Northern portion - Lop/Scatter and Prescribed Broadcast Burn; Southern portion Chip and/or pile & burn | 2018-06-20 | 67 | 41-50 | 2018-08-06 | NA | 2018-10-02 | 2018-10-02 |  | 2018-10-11 | Fix 1/20th | 2018-11-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 | 2019-09-30 |  | 2021-03-23 | Portion of unit that was handpiled was burned.
40 | Douglas-fir Mixed Conifer Treatment | 1 | 106 | 106 | 86 | Manual | Lop/Scatter and Prescribed Broadcast Burn | 2018-06-20 | 54 | 32-41 | 2017-10-28 | 2017-11-15 | 2017-10-28 | 2017-10-28 |  | 2018-10-15 | Fix 1/20th | 2018-02-14 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-23 | Portion of unit dropped to address MMG concerns and align with Rx burn. Portion of unit that was handpiled was burned.
41 | Meadow/Shrubland Restoration | 1 | 29 | 29 | 22 | Manual | Lop/Scatter and Prescribed Broadcast Burn | NA |  |  | 2017-10-28 | 2018-01-05 | 2017-10-28 | 2017-10-28 |  | NA | Fix 1/2 | 2018-02-14 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  |  | Unit was lopped and scattered (no piles to burn)
42 | Lodgepole Pine Treatment | 1 | 19 | 5.7 | 5.6 | Manual | Chip and/or pile & burn | 2018-06-20 | 149 | Patchcut | 2018-07-26 | NA | 2018-10-02 | NA |  | NA | Fix 1/50th | 2018-11-01 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20 | Removed from Phase II Mechanical to Phase 1 Manual 6/14/2018
43 | Douglas-fir Mixed Conifer Treatment | 3 | 42 | 42 | 43 | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2018-07-10 | 94 | 56-70 | 2019-06-28 | NA | 2019-07-01 | 2019-07-02 |  | 2019-08-01 | Fix 1/20th | 2019-11-20 |  | 2019-12-11 | NA | NA | 2019-11-15 | 2020-01-24 | NA | 2020-01-29 | 2020-06-03 | 2021-06-17 | 2021-07-21 | 2021-08-03
44 | Broadcast Burn |  | 198 | 198 |  | Broadcast Burn | Prescribed Broadcast Burn
45 | Douglas-fir Mixed Conifer Treatment | 1 | 131 | 131 | 118 | Manual | Lop/Scatter and Prescribed Broadcast Burn | 2018-06-20 | 53 | 32-40 | 2018-07-10 | 2018-07-23 | 2018-11-02 | NA |  | 2018-11-05 | Fix 1/20th | 2018-11-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 | 2019-10-11 |  |  | Removed from Phase II Mechanical to Phase 1 Manual 6/14/2018. Slash Tx is lop and scatter for Rx burn. Unit was lopped and scattered (no piles to burn)
46 | Ponderosa Pine Mixed Conifer Treatment | 1 | 12 | 12 | 5 | Manual | Lop/Scatter and Prescribed Broadcast Burn | 2018-06-20 | 69 | 35-40 | 2017-10-28 | 2018-01-05 | 2017-10-28 | 2017-10-28 | 2018-08-31 | 2018-09-07 | Fix 1/20th | 2018-02-14 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 | 2019-10-01 |  |  | Final Rx same as draft Rx. Unit was lopped and scattered (no piles to burn)
47 | Douglas-fir Mixed Conifer Treatment | 3 | 20 | 20 | 19 | Manual | Chip and/or pile & burn | 2018-07-10 | 61 | 37-46 | 2019-08-10 | NA | None | None |  | 2019-08-20 | Fix 1/20th | 2019-11-20 |  | 2019-12-11 | NA | NA | 2019-11-15 | 2020-01-24 | NA | 2020-01-29 | 2020-06-03 | 2021-06-17 | 2021-07-21 | 2021-08-03
48 | Ponderosa Pine Mixed Conifer Treatment | 3 | 75 | 75 | 59.5 | Manual | Chip and/or pile & burn | 2018-07-10 | 87 | 44-65 | 2019-08-17 | NA | None | None |  | 2019-09-05 | Fix 1/20th | 2019-11-20 |  | 2019-12-11 | NA | NA | 2019-11-15 | 2020-01-24 | NA | 2020-01-29 | 2020-06-03 | 2021-06-17 | 2021-07-21 | 2021-08-03
48 | Hand/Pile Burn | 5 | 11 | 11 | 11 | Manual | Chip and/or pile & burn | NA | NA | NA | 2020-08-13 | NA |  | None | None | NA | NA | 2020-10-27 |  | 2020-12-07 | NA | NA | 2020-12-07 | 2020-12-16 | NA | 2021-01-15 | [6 empty] | Hand pile previously cut portion excluded from prescribed broadcast burn (originally lop/scatter)
49 | Ponderosa Pine Mixed Conifer Treatment | 5 | 47 | 47 |  | Manual | Chip and/or pile & burn | 2018-07-10 | 59 | 30-45 | 2020-09-01 | NA |  | None |  | 2020-09-29 | Fix 1/20th | 2020-10-27 |  | 2020-12-07 | NA | NA | 2020-12-07 | 2020-12-16 | NA | 2021-01-15 | [6 empty] | Combined with Unit 73
50 | Ponderosa Pine Mixed Conifer Treatment | 1 | 7 | 7 | 6 | Manual | Chip and/or pile & burn | 2018-06-20 | 160 | 80-90 | 2017-10-17 | 2018-01-09 | 2018-08-01 | 2018-08-01 | 2018-08-09 | 2018-09-04 | Fix 1/20th | 2018-11-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 | 2020-01-29 |  | 2021-03-20
51 | Ponderosa Pine Mixed Conifer Treatment | 1 | 89 | 89 | 79 | Manual | Chip and/or pile & burn | 2018-06-20 | 66 | 35-40 | 2017-10-17 | 2018-02-09 | 2018-08-01 | 2018-08-01 |  | 2018-08-29 | Fix 1/20th | 2018-11-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 | 2020-01-30 |  | 2021-03-20 | Final Rx same as draft Rx.
52 | Ponderosa Pine Mixed Conifer Treatment | 5 | 8 | 8 | 6 | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2020-06-02 | 81 | 41-49 | 2020-06-09 | NA |  | None |  | 2020-06-17 | Fix 1/20th | 2020-10-27 |  | 2020-12-07 | NA | NA | 2020-12-07 | 2020-12-16 | NA | 2021-01-15
53 | Aspen Restoration | 5 | 16 | 16 | 14 | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2020-05-28 | 58 |  | 2020-08-14 | NA |  | None |  | 2020-08-14 | Fix 1/20th | 2020-10-27 |  | 2020-12-07 | NA | NA | 2020-12-07 | 2020-12-16 | NA | 2021-01-15
54 | Mixed Conifer Treatment OG | 5 | 18 | 18 | 4 | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2020-06-02 | 73 | 51-55 | 2020-06-09 | NA |  | None |  | 2020-06-17 | Fix 1/20th | 2020-10-27 |  | 2020-12-07 | NA | NA | 2020-12-07 | 2020-12-16 | NA | 2021-01-15 | [6 empty] | Combined with Unit 55
55 | Douglas-fir Mixed Conifer Treatment | 5 | 5 | 5 | 6 | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2020-06-02 | 71 | 50-53 | 2020-06-09 | NA |  | None |  | 2020-06-17 | Fix 1/20th | 2020-10-27 |  | 2020-12-07 | NA | NA | 2020-12-07 | 2020-12-16 | NA | 2021-01-15 | [6 empty] | Combined with Unit 54
58 | Lodgepole Pine Treatment |  | 26 | 7.8 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-07-10 | 64
59 | Douglas-fir Mixed Conifer Treatment |  | 14 | 14 |  | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-07-10 | 70
60 | Douglas-fir Mixed Conifer Treatment |  | 5 | 5 |  | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-07-10 | 119
61 | Aspen Restoration | 5 | 7 | 7 | 5 | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2020-07-31 | 61 |  | 2020-07-29 | NA |  | None |  |  | Fix 1/20th | 2020-10-27 |  | 2020-12-07 | NA | NA | 2020-12-07 | 2020-12-16 | NA | 2021-01-15 | [6 empty] | PP > 14" DBH still need to be identified to NOT cut
63 | Ponderosa Pine Mixed Conifer Treatment |  | 5 | 5 | 2 | Manual | Chip and/or pile & burn | 2018-06-20 | 74 |  | 2018-08-29 | NA | 2018-11-02 | NA |  | NA | Fix 1/20th | 2018-11-07 |  | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [7 empty] | Unit delayed - decision by Angie 3/13/2019
67 | Aspen Restoration |  | 13 | 13 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-07-09 | 54
68 | Douglas-fir Mixed Conifer Treatment | 3 | 10 | 10 | 9.5 | Manual | Chip and/or pile & burn | 2018-07-10 | 121 | 73-90 | 2019-08-05 | NA | 2019-08-07 | None |  | 2019-08-22 | Fix 1/20th | 2019-11-20 |  | 2019-12-11 | NA | NA | 2019-11-15 | 2020-01-24 | NA | 2020-01-29 | 2020-06-03 | 2021-06-17 | 2021-07-21 | 2021-08-03 |  |  | Removed from Phase II Mechanical to Phase 3 Manual 6/14/2018
73 | Ponderosa Pine Mixed Conifer Treatment | 5 | 76 | 76 |  | Manual | Chip and/or pile & burn | 2018-07-10 | 84 | 42-63 | 2020-09-01 | NA |  | None |  | 2020-09-29 | Fix 1/20th | 2020-10-27 |  | 2020-12-07 | NA | NA | 2020-12-07 | 2020-12-16 | NA | 2021-01-15 | [6 empty] | Combined with Unit 49
74 | 2-Staged Mixed Conifer Treatment (Stage 1) | 1 | 44 | 44 | 37 | Manual | 1) pile & burn | NA | 116 | NA | 2017-10-05 | 2018-07-27 |  | NA |  | NA | NA | NA | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2020-03-10 | Step Transect not provided for Stage 1 (piling) activity. Step Transect will be completed prior to thinning operation. Repainted to exclude drainage and riparian vegetation
74 | 2-Staged Mixed Conifer Treatment (Stage 2) | 5 | 44 | 44 | 38 | Manual | 2) thin and pile & burn |  | 116 | 70-81 | 2020-08-26 | NA |  | None |  | 2020-09-29 | Fix 1/20th | 2020-10-27 |  |  | NA | NA | 2020-12-07 | 2020-12-16 | NA | 2021-01-15
75 | Lodgepole Pine Treatment | 1 | 14 | 4.2 | 2.5 | Manual | Chip and/or pile & burn | 2018-06-20 | 116 | Patchcut | 2018-07-26 | NA | 2018-10-02 | NA |  | NA | Fix 1/50th | 2018-11-01 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20 | Removed from Phase II Mechanical to Phase 1 Manual 6/14/2018
76 | Lodgepole Pine Treatment | 1 | 12 | 3.6 | 3.4 | Manual | Chip and/or pile & burn | 2018-06-20 | 123 | Patchcut | 2018-07-26 | NA | 2018-10-02 | NA |  | NA | Fix 1/50th | 2018-11-01 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
77 | Douglas-fir Mixed Conifer Treatment |  | 269 | 269 |  | Mechanical/ Manual | Remove off-site and/or chip and/or masticate and/or pile & burn
80 | Douglas-fir Mixed Conifer Treatment | 5 | 8 | 8 |  | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2020-05-29 | 83 | 58-62 | 2020-06-09 | NA |  | None |  | 2020-10-05 | Fix 1/20th | 2020-10-27 |  | 2020-12-07 | NA | NA | 2020-12-07 | 2020-12-16 | NA | 2021-01-15 | [6 empty] | Thin and aspen aggregations
81 | Aspen Restoration |  | 12 | 12 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn
82 | Regeneration Thin | 1 | 1 | 1 | 0.9 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | 2017-12-05 |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
83 | Regeneration Thin | 1 | 0.4 | 0.4 | 0.4 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
84 | Regeneration Thin within Defensible Space | 1 | 0.3 | 0.3 | 0.3 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
85 | Regeneration Thin | 1 | 1 | 1 | 0.63 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20 | Unit Dropped - Not enough trees (12/5/2017); re-evaluated as aspen enhancement due to aspen dominance in patchcuts (6/14/2018)
86 | Regeneration Thin | 1 | 1 | 1 | 0.55 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20 | Unit Dropped - Not enough trees (12/5/2017); re-evaluated as aspen enhancement due to aspen dominance in patchcuts (6/14/2018)
87 | Regeneration Thin within Defensible Space | 1 | 0.5 | 0.5 | 0.33 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
88 | Regeneration Thin within Defensible Space | 1 | 0.4 | 0.4 | 0.25 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
89 | Regeneration Thin | 1 | 1 | 1 | 0.52 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
90 | Regeneration Thin | 1 | 0.5 | 0.5 | 0.36 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
90a | Regeneration Thin within Defensible Space | 1 | 0.5 | 0.5 | 0.05 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
91 | Regeneration Thin within Defensible Space | 1 | 0.6 | 0.6 | 0.52 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
92 | Regeneration Thin | 1 | 0.5 | 0.5 | 0.4 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
92a | Regeneration Thin within Defensible Space | 1 | 0.5 | 0.5 | 0.02 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
93 | Regeneration Thin | 1 | 0.5 | 0.5 | 0.32 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
94 | Regeneration Thin | 1 | 1 | 1 | 0.51 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
95 | Regeneration Thin | 1 | 0.4 | 0.4 | 0.4 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
96 | Regeneration Thin | 1 | 2 | 2 | 2 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
97 | Regeneration Thin | 1 | 1 | 1 | 1.15 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
98 | Regeneration Thin | 1 | 0.3 | 0.3 | 0.3 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
99 | Regeneration Thin | 1 | 2 | 2 | 2.31 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20
100 | Regeneration Thin | 1 | 0.5 | 0.5 | 0.5 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20 | Unit Dropped - Not enough trees (12/5/2017); re-evaluated as aspen enhancement due to aspen dominance in patchcuts (6/14/2018). Combined w/ unit 100a in layout
100a | Regeneration Thin within Defensible Space | 1 | 0.5 | 0 | 0 | Manual | Chip and/or pile & burn | NA | NA |  | 2017-12-05 | NA | 2017-12-05 | Unit 82 SM |  | NA | Fix 1/100th | 2018-02-07 | Completed | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | 2019-03-18 | 2019-06-20 | 2019-08-01 | 2019-09-27 |  |  | 2021-03-20 | Unit Dropped - Not enough trees (12/5/2017); re-evaluated as aspen enhancement due to aspen dominance in patchcuts (6/14/2018). combined w/ unit 100 in layout
101 | Lodgepole Pine Treatment |  | 39 | 11.7 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-07-08 | 94
102 | Aspen Restoration | 3 | 11 | 11 | 8.5 | Manual | Chip and/or pile & burn or lop/scatter | 2019-09-13 | 91 |  | 2019-09-10 | NA | None | NA |  | NA | Fix 1/20th | 2019-11-18 |  | 2019-12-11 | NA | NA | 2019-11-15 | 2020-01-24 | NA | 2020-01-29 | 2020-06-03 | 2021-06-17 | 2021-07-21 | 2021-08-03
103 | Lodgepole Pine Treatment | 3 | 20 | 6 | 5 | Manual | Chip and/or pile & burn | 2019-09-13 | 70 | Patchcut | 2020-10-17 | NA | None | NA |  | NA | Fix 1/50th | 2019-11-18 |  | 2019-12-11 | NA | NA | 2019-11-15 | 2020-01-24 | NA | 2020-01-29 | 2020-06-03 | 2021-06-17 | 2021-07-21 | 2021-08-03
104 | Ponderosa Pine Mixed Conifer Treatment |  | 8 | 8 |  | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-07-10 | 39
105 | Ponderosa Pine Mixed Conifer Treatment |  | 12 | 12 |  | Manual | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-07-09 | 70
106 | Aspen Restoration |  | 18 | 18 |  | Mechanical | Remove off-site and/or chip and/or masticate and/or pile & burn | 2019-07-09 | 57
107 | Lodgepole Pine Treatment |  | 5 | 1.5 | 1 | Manual | Chip and/or pile & burn | 2018-07-10 | 100 |  | 2018-08-29 | NA | 2018-11-02 | NA |  | NA | Fix 1/50th | 2018-11-01 |  | 2018-12-21 | NA | NA | 2018-12-21 | 2019-01-29 | NA | [7 empty] | Unit delayed - decision by Angie 3/13/2019
GPS acres rounded except for Lodgepole Pine Treatment and Regeneration Thin Units
Phase 1
Phase 2
Phase 3
Phase 4
Phase 5
Delayed