|  |  |  |
| --- | --- | --- |
| ***Adaptive Management******Themes*** | ***What Steps Have Been Taken to Meet Theme Objectives*** | ***Suggested Recommendations for Improving Theme Objectives*** |
| *Increase public engagement and**outreach* | \*GMUG produces an annual “community report” on SBEADMR in “plainspeak” language for the public\*Format of annual stakeholder meeting recognizes different levels of audiences and levels of information desired by each\*CFRI SBEADMR website (repository and archive for all SBEADMR AMG related meetings and documents for public access)\*District Rangers/Timber staff willing to meet/host field trips with local community stakeholders on specific treatment projects when requested\* Introduced a “Story Map” in 2021 for public toreview and comment electronically on proposed treatment sites and prescriptions. | \*Engage with groups that have not historically been involved, e.g., CPW, CO Wildfire Council, Bureau of Reclamation, DNR\*Reduce turnover and vacancies in AMG/FS staff\*Consider membership composition of AMG\*Increase new and traditional modes of communicating with the public\*More opportunities to engage with communities and District Ranger/Staff\*County Commissioner representation on field trips\*Hire a communication specialist or coordinator |
| *Shared learning, understanding and transparency* | \*Annual SBEADMR Stakeholder meeting\*AMG Implementation Matrix links SBEADMR ROD’s goals with Science Team findings, AMG recommendations and FLT decisions\*SBEADMR Science Team’s annual report of research/monitoring activities\*SBEADMR Summer field trips with Science Team/GMUG staff; field trip notes produced and posted on CFRI SBEADMR website\*Outside expertise invited to address certain topics of interest/concern for the AMG membership, e.g., PONSSE, CTL, PODS, RADS, etc. | \*Field trips: pre- and post- treatment – in same location; debriefs\*Shared understanding of resilience concept in context of SBEADMR\*Process for integrating scientific information brought to the group\*Be more transparent about how science informs lynx management and mitigation\*Develop onboarding processes for new participants |

|  |  |  |
| --- | --- | --- |
| **Adaptive Management****Themes** | **What Steps Have Been Taken to Meet Theme Objectives** | **Recommendations for Improving Theme Objectives** |
| *Collaboration throughout the process* | \*AMG Operations Manual \*Convene regularly scheduled meetings of AMG with GMUG staff and Science Team participation\*AMG Monitoring Committee works in conjunction with GMUG staff and Science Team to research and refine issues for AMG consideration and/or recommendation | \*Provide more detail on planned treatments during out-year planning\*Increase opportunities for dialogue with AMG, FLT concerning what adaptions were made, and why or why not\*Enhance communication internally with GMUG staff  |
| *Outputs and outcomes* | \*Science Team is assessing the adaptive management and public engagement processes throughout the life of SBEADMR and reports regularly at AMG meetings\*Other spin-offs of SBEADMR - Taylor Park EA AMG - Wilder - NFF Partnering with GMUG | \*Evaluate success and challenges of process and document SBEADMR model of collaborative adaptive management in reports, blogs, publications\*Enhance readiness to receive increased state and federal funding for wildfire mitigation - link to wildfire risk monitoring, decision-support(PODS) pivot towards fuel mitigation and fiber harvest |